CSPCWG3-3A

3rd CSPCWG Meeting

Monaco, 22-24 November 2006

CSPCWG 2 ACTIONS

(updated to 11 October 2006)

s

| No | Action | Delegate | Status |
| --- | --- | --- | --- |
| 1 | Produce draft report of CSPCWG 2 by end November 2005 in accordance with the Chairman’s instructions, for participants to approve. | Sec | Completed |
| 2 | Supply any internal or published guidance on chart maintenance to the Secretary to help draft M-4 entry, by end of January 2006. Action 15 from CSPCWG 1 carried forward until end January 2006. Recd from AU, DE, FR | All WG members | Completed |
| 3 | Add revised TOR to IHO website. | M Huet | Completed |
| 4 | Improve links to M-4 on CSPCWG web page. Link exists, sometimes slow to open. | M Huet |  |
| 5 | Discuss within IHB whether M-4 & M-11 can be made ‘free’. Included in M-4 Edition 3.003 M-4 marked ‘free’, M-11 not yet available | M Huet |  |
| 6 | Examine CSPCWG web-page, and provide suggestions for improvements to Secretary and IHB by end February 2006 | All WG members | Time expired |
| 7 | Discuss resourcing for M-4 translation. | IHB, FR, CA & ES |  |
| 8 | Prepare paper for discussion by WG on status of INT 1, 2, 3, for presentation to CHRIS 18 (Sept 2006). Sent to CHRIS 21 July2006 | Sec, Chair | Completed |
| 9 | Prepare a Letter on the ‘Principles for Portraying Maritime Limits’ as drafted at CSPCWG 2, for further discussion by WG. Included in Annex D to CSPCWG2 report and covering letter to CSPCWG2 Report | Sec, Chair | Completed |
| 10 | Include UK’s brief on Territorial limits as annex to CSPCWG2 Report and note sub-section B-440 for including during review. See Annex E to CSPCWG2 report | Sec | Completed |
| 11 | Consider CSPCWG2 discussion on Fairways and develop proposal further in consultation with Chair and Secretary, for inclusion within revision of B-430 to 439. Include in B430 round 3 | FI, Chair, Sec | Continuing |
| 12 | Brief the S-32 WG (via S Shipman at IHB) on the various terms used in Ships’ Routeing. Letter sent to S Shipman 09/11/05 | Sec | Completed |
| 13 | Note M-4 specifications B-370.8 (for refuge) and B-353.8 and B-449.1 (for ice limit date) for inclusion during the on-going revision. | Sec | Completed |
| 14 | Advise IHB of outcome (by letter to HCA Secretary - M Huet), including reference to ‘Glacier’ symbol in advance of HCA (2 November 2005). Letter sent 26/10/05 | Chair | Completed |
| 15 | Advise HCA that the WG accepted the recommendations of the CSPCWG Chairman. | M Huet |  |
| 16 | Invite WG members to contribute colour mix percentages for use in ‘examples annex’ in M-4 B-100. Included in covering letter to CSPCWG2 Report | Sec | Completed |
| 17 | Supply dimensions of reporting line symbol to Secretary. Included in covering letter to CSPCWG2 Report | DE | Completed |
| 18 | Draft Letter outlining Reporting line proposals (to include explanations of VTS, reporting points, areas), for consideration by full WG, TSMAD and C&SMWG. Included in covering letter to CSPCWG2 Report | Sec, Chair, FI | Completed |
| 19 | Draft Letter to WG members, TSMAD and C&SMWG re proposal for abbreviation ‘(sync)’. To include consideration of location in INT 1. Included in covering letter to CSPCWG2 Report | Sec, Chair | Completed |
| 20 | Contact IALA (via Trinity Ho) to advise of proposal (sync). Email sent 18/01/06. Awaiting IALA response, chased 17/08/06 | Sec | Completed |
| 21 | Include coloured version of oscillating light sectors at INT 1 P30.3 (at next revision). Included in FR draft | DE, FR, ES |  |
| 22 | Note M-4 B-475.7 to include explanation of PEL and methods of depiction for oscillating PEL and to advise TSMAD and C&SMWG. Included in covering letter to CSPCWG2 Report | Sec | Completed |
| 23 | Draft Letter to WG members, TSMAD and C&SMWG, re proposal for DGPS stations, to include suggested placement of specification in M-4. Included in covering letter to CSPCWG2 Report | Sec, Chair | Completed |
| 24 | Include Bo as Nature of seabed in M-4 B-425.5 revision, with ‘(usually used in intertidal areas)’ comment. Included in M-4 Edition 3.003 | Sec | Completed |
| 25 | Add Bo as Nature of seabed at INT 1 J9.1 and sections V and W (at next revision). After meeting note: R to be 9.1, Bo to be 9.2 (as M-4 v3.003). Included in FR draft. | DE, FR, ES |  |
| 26 | Note B-300 for inclusion of solitary, conspicuous boulders, for inclusion at revision. Noted to probably include at B-312.5 | Sec | Completed |
| 27 | Include revised wording for B-131 in draft IHO CL for M/S approval of B-400 to B-429. Included in IHO CL 30-2005. Now included in M-4 Edition 3.003 | Sec | Completed |
| 28 | Remove the 2nd paragraph of B-302 at the next revision of M-4. Removed from M-4 version 3.002 | Sec | Completed |
| 29 | Draft additional wording in B-422.5-.7 (Wrecks) to include FR proposal. Included in B-400 to B-429 Round 4 (Ltr 16/05) | Sec | Completed |
| 30 | Include further amendments to B-400-429 as discussed, and circulate to WG as ‘Round 4’. Ltr 16/05 | Sec | Completed |
| 31 | Collaborate on revised preface to M-11. Email exchange 27-31/01/06 | Sec, M Huet | Completed |
| 32 | Consider whether DE, FR & ES INT 1 versions can be placed on IHO website. | DE, FR, ES |  |
| 33 | Respond to Brazil regarding INT 1 (in consultation with DE). Email sent 21/11/05 | Chair | Completed |
| 34 | NMs for INT 1 – DE, FR, ES to advise Secretary and IHB so CL can be issued. IHO CL 47/2006 refers | DE, FR, ES | Completed |
| 35 | Enquire whether a low resolution version of INT 3 could be made available for the IHO website. Licence and CD sent to IHB 12/05 | Sec | Completed |
| 36 | Update Work Plan as discussed and include in report (see Annex F). | Sec | Completed |
| 37 | Respond to IHB re marking of wind farms, for IHO’s formal response to IALA. Sent to IHB 15/12/05 (& forwarded to IALA) | Chair | Completed |
| 38 | Raise IALA paper at TSMAD12 (November 2005) Raised as Item 12 in paper TSMAD12-8.4A | AU | Completed |
| 39 | Include a paragraph to increase visibility to the WG’s activities and as a means of seeking maximum involvement of M/S in next appropriate IHO CL. Included in IHO CL 121/2005 of 6/12/05 | M Huet | Completed |
| 40 | Consider whether to offer to host CSPCWG3, and advise Secretary by 26/01/06. No offers received. CSPCWG3 therefore in Monaco. | All WG members | Completed |