## Taul1
Action item code | WP | Item | Deliverable | Delivery date | Delivery to | Person responsible | Persons involved | Products affected | WG affected
1 | H.1 | Suggest new attributes to S-100 registry and S-101 DCEG to clarify deep water routes and swept areas | Paper | 1 July | S-101PT | Sean Legeer |  | S-101
2 | H.1 | Include temporal variation guidance to DCEG and make the DCEG text consistent | DCEG text on temporal variation | 1 July | S-101PT | Rogier Broekman | Sean Legeer
3 | H.1 | Fuzzy areas | Response | 1 October | NIPWG and its subgroups | Edward Hosken |  | S-122 |  | HSSC task
4 | H.1 | DSCC views | Response | 1 August | DPSWG, HSSC8 | Antti |  |  |  | HSSC task
5 | H.1 | Review S-101 DCEG DQ section | Comments on DCEG DQ section | 31 December | S-101PT | Eivind | Group | S-101 | S-100, S-101PT
6 | I.1 | Report to HSSC8 | Report and presentation | 15 Sept 2016 | HSSC8 | Antti Castrén
7 | H.1 | Add dataset level attributes and time and speed unc. to data model and review | Data model | 31 December | S-101PT | Eivind
8 | B.4 | Hierarchy and decision tree | Decision tree | 15 September 2016 | S-101PT | Antti Castrén
9 | B.4 | Paper to NCWG on stacked quality display on paper charts and S-101 ENCs and textual explanation of classes |  | 1 July | NCWG | Mike Prince |  | S-101, S-4
10 | C.4 | AC to send the DQ texts to RB and MP | DQ texts from CH | 31 May | Rogier and Mike | Antti Castrén
11 | C.4 | RB and MP and BH to compile mariners education texts (What and How) | First draft | 22 June 2016 | Bowditch | Rogier | Mike, Brian
12 | H.1 | RB rewrite stacked DQ guidance for S-101 DCEG and add mobile seafloor perspective |  | 31 December
13 | H.1 | RB rewrite temporal variation guidance S-101 DCEG |  | 31 May |  | Rogier
14 | I.1 | Paper on IHO strategic plan and work programme | DQWG response | 14 May 2016 |  | Antti Castrén | Edward Hosken
15 | H.1 | Update feature and attribute definitions in GI registry |  | 31 December |  | Eivind
16 | H.1 | Review applicability of the enumerated values of temporal variation for QoNBD | Draft | 15 July | DQWG | Sean Legeer
17 | A.1 | Review S-100 section 4C and INSPIRE and ISO standards | Paper | 1 Sept 2016 | DQWG | Rogier Broekman | Sean Legeer
18 | I.1 | Update roadmap after chair group meeting | Road map | 22 June 2016 |  | Antti Castrén