DRAFT CONSOLIDATED HSSC WORK PLAN 2015-2016

Draft Version 31 October 2014

Notes:

a/ This draft consolidated work plan (WP) has been compiled from the reports submitted to HSSC-6.

b/ Tasks that should be confirmed at HSSC-6 as, either “completed” in 2014 (so to be deleted from 2015-2016 WP), or “continuing “ in 2015.

c/ The final version will reflect the decisions from HSSC-6.

Objective:

This work plan aims at ensuring efficient project resource management and alignment, progress monitoring and to provide a communication utility with internal and external parties.

Rationale:

The justification for the HSSC Work Plan is in conformance with the IHO Strategic Plan, and mainly related to the following elements of the IHO Work Programme – 2013-2017:

Element 2.1 Technical Programme Coordination Element 2.2 Hydrographic Data Transfer Standards Element 2.3 Nautical Cartography

Element 2.4 Digital Data Protection and Authentication

Element 2.5 Data Quality

Element 2.6 Nautical Publications Element 2.7 Tides and Datums Element 2.8 Digital Data Updating

Element 2.9 Marine Spatial Data Infrastructures

Element 2.10 Hydrographic Data Acquisition and Processing

Element 2.11 Hydrographic Dictionary

Element 2.12 Hydrographic Aspects of UNCLOS Element 2.13 Surface Current

Procedure:

The HSSC work plan covers a rolling two year period and is revised annually.  Each subordinate body proposes in its report to the annual meeting of HSSC a revised work plan for the next biennium.  Completed work items should be removed from work plans after they have been reported at a subsequent HSSC meeting.  The Chairs of the subordinate bodies, along with the HSSC Chair, will meet prior to each HSSC meeting to review progress, and to harmonize the proposed work plans.  The proposed work plans for the next biennium will be considered by the plenary with the report of each subordinate body.  The draft consolidated HSSC work plan for the next biennium will be reviewed on the last day of the HSSC meeting, incorporating the agreed changes discussed during that meeting.  A revised consolidated HSSC work plan incorporating all approved additional work items will be circulated to participants of the meeting for final comment at the same time as the draft minutes of the meeting. HSSC Chair could seek committee members’ interim approval for emerging issues between meetings.

Communications:

The HSSC Work Plan will be posted on the IHO website, and a progress summary will be provided at IHO Conferences/Assemblies.

Monitoring:

In accordance with Decision No. 3 of the 5th Extraordinary International Hydrographic Conference (EIHC-5), the HSSC Chair and the Chairs of subordinate bodies will be invited “to report, twice annually at year-end and mid-year, on the overall status of their respective work programmes by completing a simple, two-part template that requests brief lists of a) current goals and priorities, and b) current or expected gaps and needs.”

Project Numbering:

Each task will be given a sequential number independent of related subordinate body. The related IHO Work Programme Element number and the specific HSSC meeting that approved the inclusion of the task will be identified in the HSSC Work Plan summary.    Each sub task will be numbered using an alphanumeric sequence, “An, Bn, Cn..”

Priorities:

Three Levels of Priorities (H, M, and L) will be assigned by HSSC using the “Guidelines for the Evaluation of

Proposed New Work Items for HSSC and its Subordinate Bodies” (see section 1 hereafter).

1.	GUIDELINES FOR THE EVALUATION OF PROPOSED NEW WORK ITEMS FOR HSSC AND ITS SUBSIDIARY BODIES

Introduction

1.1	In order to best use the limited resources available to HSSC and its subordinate bodies, it is necessary to evaluate and prioritise proposed new work items.   These guidelines are based on the principles originally agreed at CHRIS/13 and CHRIS/15 and revised and enhanced at CHRIS/18.   They are intended to provide a uniform basis for evaluation and prioritisation.

1.2	Evaluation should be done as a two-stage process:

a.	general consideration leading to acceptance or rejection; and if accepted,

b.	establishment of priorities.

General acceptance

1.3	Before deciding to include a new item in the work plan of HSSC and its subordinate bodies, the following factors should be taken into account:

a.	is the subject addressed by a proposal considered to be within:

(1)	the scope of IHO objectives?

(2)	the current IHO work programme?

b.	has a need for the measure proposed been identified (for example, client demand, internal improvements)?

c.	do adequate industry standards or solutions exist or are they being developed thereby reducing the need for action through HSSC and its subordinate bodies?

d.	is the objective achievable in the existing HSSC and its subordinate bodies‟ work plan taking into account a realistic estimates of resources needed and available?

e.	what are the envisaged deliverables?

Establishment of priorities

1.4	Priorities for accepted work items should normally be assigned based on consideration of the following factors:

a.	measures aimed at  substantially preventing maritime casualties, marine pollution incidents or enhancing maritime security

b.	measures to overcome identified deficiencies in existing IHO standards and technical resolutions;

c.	measures needed to align IHO standards and resolutions with those of other relevant international standards and recommendations;

d.	measures required to take into account the introduction of new technologies and methods in maritime operations;

e.	measures  required  to  take  into  account  new  techniques  in  data  acquisition, processing and management, and production techniques in hydrography;

f.	measures leading to increased Hydrographic Office efficiency.

1.5	Follow up actions in response to specific requests from the International Hydrographic Conference or other international and intergovernmental organisations should be evaluated in light of paragraph 1.4 above unless specifically identified as urgent matters.

General remarks

1.6	When setting priorities, certain flexibility should be provided to allow for initiatives that could not be foreseen.

1.7	Once a decision has been made on the basis of the above for a new work item to be included in the work plan of HSSC and its subordinate bodies, an appropriate target completion date should be established, taking into account the urgency of the matter concerned.

1.8	In general, proposals for new work items as well as the revised work plans presented by Chairs of subordinate bodies as part of their annual reports should include a proposed priority for each work item, based on the guidelines above.

1.9	Wherever possible, proposed priorities for work items will be considered ahead of a meeting by a “Chair Group” comprising Chair, Vice-Chair, Secretary and all available Chairs of subordinate bodies.   Final endorsement of work item priorities will rest with HSSC and be considered at the respective meeting.

2.	HSSC RELEVANT ELEMENTS OF IHO WORK PROGRAMME 2013-2017

All elements described below  (taken from  IHC XVIII document CONF.18/REP/01 and updated in accordance with EIHC-5 document CONF.EX5/REP.04 - Annex B - Appendix 1) relate to  Programme 2 “Hydrographic Services and Standards”,  which seeks to develop, maintain and extend technical standards, specifications and guidelines to enable the provision of standardised products and services that meet the requirements of mariners and other users of hydrographic information.

These elements will be completed when deemed necessary after consideration by HSSC of the Decisions of the EIHC-5 (HSSC6-04.3A refers).

Element 2.1 Technical Programme Coordination

Objective: To monitor technical developments, oversee the development of IHO technical standards, specifications and publications through the coordination and interaction of relevant IHO Working Groups, and to make recommendations to Member States.

| Task 2.1.1 | Conduct annual meetings of HSSC | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.1.2 | Provide technical advice and guidance on IHO technical standards, specification and publications | 2013-17 |  |

Element 2.2 Hydrographic Data Transfer Standards

Objective: To monitor developments related to transfer standards for digital hydrographic data, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.2.1 | Conduct annual and biennial meetings of relevant HSSC WGs dealing with hydrographic data transfer standards | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.2.2 | Maintain and extend the relevant IHO standards, specifications and publications, using contract support assistance as appropriate, including: - S-57 IHO Transfer Standard for Digital Hydrographic Data - S-100 IHO Universal Hydrographic Data Model - S-101 ENC Product Specification - S-102 Bathymetric Surface Product Specification - S-58 Recommended ENC Validation Checks - S-65 ENC Production Guidance - S-64 IHO Test Data Sets for ECDIS - S-61 Product Specification for Raster Navigational Charts - S-99 Operational Procedures for the Organization and Management of the S-100 Geospatial Information Registry - S-66 Facts about Electronic Charts and Carriage Requirements - RENC Joint Technical Experts WG | 2013-17 | Contract support: 15K€ each year |
| Task 2.2.3 | Develop and maintain as-yet undefined S-100-based Product Specifications | 2013-14 |  |
| Task 2.2.4 | Maintain and extend S-100 registry | 2013-17 | no significant IHO expense anticipated |
| Task 2.2.5 | Provide outreach and technical assistance regarding transfer standards | 2013-17 |  |

Element 2.3 Nautical Cartography

Objective: To monitor developments related to nautical cartography for paper nautical charts and the colours, symbols and display rules used to show SENC information on ECDIS, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.3.1 | Conduct meetings of relevant HSSC WGs dealing with nautical cartography | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.3.2 | Maintain and extend the relevant IHO standards, specifications and publications, using contract support assistance as appropriate, including: - S-4 Chart Specifications of the IHO and Regulations for International (INT) Charts INT 1 - Symbols, Abbreviations and Terms used on Charts INT 2 - Borders, Graduations, Grids and Linear Scales INT 3 - Use of Symbols and Abbreviations - S-11 Part A - Guidance for the Preparation and Maintenance of INT Chart schemes - S-11 Part B - Catalogue of INT Charts - S-49 Standardization of Mariners' Routeing Guides - Digital data updating related elements of Appendix 1 to S-52 - Guidance on Updating the Electronic Navigational Chart - S-52 and its accompanying Presentation Library - Specifications for Chart Content and Display Aspects of ECDIS - Portrayal related elements of S-101 - ENC Product Specification and other S-100-based Product Specifications | 2013-17 | Contract support: 15K€ each year |

Element 2.4 Digital Data Protection and Authentication

Objective: To monitor developments related to data protection and data authentication, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.4.1 | Conduct meetings of relevant HSSC WGs dealing with data protection and authentication | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.4.2 | Maintain and extend the relevant IHO standards, specifications and publications, including: - S-63 IHO Data Protection Scheme - Data protection and authentication related elements of S-100 - IHO Universal Hydrographic Data Model and - S-101 - ENC Product Specification | 2013-17 | no significant IHO expense anticipated |

Element 2.5 Data Quality

Objective: To monitor developments related to methods of classifying and depicting the quality of hydrographic information, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.5.1 | Conduct meetings of relevant HSSC WG dealing with data quality | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.5.2 | Maintain and extend the relevant IHO standards, specifications and publications, including: - Data quality related elements of S-57 - IHO Transfer Standard for Digital Hydrographic Data - Data quality related elements of S-52 - Specifications for Chart Content and Display Aspects of ECDIS - Data quality related elements of S-100 - IHO Universal Hydrographic Data Model and - S-101 - ENC Product Specification and other S-100-based Product Specifications | 2013-17 | no significant IHO expense anticipated |

Element 2.6 Nautical Publications

Objective: To monitor developments related to the preparation of nautical publications, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.6.1 | Conduct meetings of relevant HSSC WG dealing with nautical publications | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.6.2 | Develop, maintain and extend S-10n - Nautical Information Product Specification | 2013-17 | no significant IHO expense anticipated |
| Task 2.6.3 | Maintain and extend the relevant IHO standards, specifications and publications, including: - IHO Resolutions in M-3 relating to Nautical Publications - S-12 Standardization of List of Lights and Fog Signals | 2013-17 | no significant IHO expense anticipated |

Element 2.7 Tides and Datums

Objective: To monitor developments related to tidal and water level observation, analysis and prediction and other related information including vertical and horizontal datums, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.7.1 | Conduct meetings of relevant HSSC WG dealing with tides and water levels | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.7.2 | Maintain and extend the relevant IHO standards, specifications and publications, including: - Relevant IHO Resolutions in M-3 - S-60 User´s Handbook on Datum Transformations involving WGS 84 - Standard Tidal Constituent List - Inventory of Tide Gauges used by Member States | 2013-17 | no significant IHO expense anticipated |
| Task 2.7.3 | Develop, maintain and extend a Product Specification for digital tide tables | 2013-17 | no significant IHO expense anticipated |
| Task 2.7.4 | Develop, maintain and extend a Product Specification for the transmission of real-time tidal data | 2013-17 | no significant IHO expense anticipated |
| Task 2.7.5 | Develop, maintain and extend a Product specification for dynamic tides in ECDIS | 2013-17 | no significant IHO expense anticipated |

Element 2.8 Digital Data Updating

Objective: To monitor developments in standardized processes for the updating of digital hydrographic data products, to develop and maintain the relevant IHO standards, specifications and publications, and to provide technical advice as appropriate.

| Task 2.8.1 | Maintain and extend the relevant IHO standards, specifications and publications, including: - Digital data updating related elements of S-65 - ENC Production Guidance - S-52 Appendix 1 - Guidance on Updating the Electronic Navigational Chart | 2013-17 | no significant IHO expense anticipated |
| --- | --- | --- | --- |

Element 2.9 Marine Spatial Data Infrastructures

Objective: To monitor developments related to the hydrographic component of Spatial Data Infrastructures, to develop and maintain the relevant IHO publications, and to provide technical advice as appropriate.

| Task 2.9.1 | Conduct meetings of relevant HSSC WG dealing with MSDI | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.9.2 | Maintain the relevant IHO standards, specifications and publications, including: - C-17 Spatial Data Infrastructures: “The Marine Dimension” - Guidance for Hydrographic Offices | 2013-17 | no significant IHO expense anticipated |
| Task 2.9.3 | Develop training syllabi for MSDI and associated learning subjects |  |  |

Element 2.10 Hydrographic Data Acquisition and Processing

Objective: To monitor developments related to hydrographic data acquisition and processing, to develop and maintain the relevant IHO publications, and to provide technical advice as appropriate.

| Task 2.10.1 | Conduct annual meetings of relevant HSSC WG dealing with hydrographic data acquisition and processing (currently S-44WG) | 2013-17 | no meetings planned at present (when WG required) |
| --- | --- | --- | --- |
| Task 2.10.2 | Maintain and extend, when required, the relevant IHO standards, specifications and publications, including: S-44 - IHO Standards for Hydrographic Surveys | 2013-17 | no meetings planned at present |

Element 2.11 Hydrographic Dictionary

Objective: To develop, maintain and extend S-32 - Hydrographic Dictionary in English, French and Spanish and to provide technical advice as appropriate.

| Task 2.11.1 | Maintain and extend the IHO Hydrographic Dictionary in English, French and Spanish | 2013-17 | no significant IHO expense anticipated |
| --- | --- | --- | --- |
| Task 2.11.2 | Develop the Spanish language Wiki version of S-32 with commercial contract support | 2013-14 | contract support: 20K€ |

Element 2.12 Hydrographic Aspects of UNCLOS

Objective: To monitor developments related to the hydrographic aspects of the UN Convention on the Law of the Sea, to develop and maintain the relevant IHO publications, and to provide technical advice as appropriate.

| Task 2.12.1 | Organize and prepare ABLOS annual business meeting | 2013-17 |  |
| --- | --- | --- | --- |
| Task 2.12.2 | Organize and prepare the biennial ABLOS Conference | 2014-16 | self-funding |
| Task 2.12.3 | Contribute to the revision of IHO publication C-51- TALOS Manual | 2013-17 | no significant IHO expense anticipated |

Element 2.13 Surface Current

Objective: To develop standards for the delivery and presentation of navigationally relevant current information.

| 2.13.1 | Conduct meetings of relevant HSSC WGs dealing with surface currents | 2013-17 |  |
| --- | --- | --- | --- |
| 2.13.2 | Maintain and extend the relevant IHO standards, specifications and publications, including: | 2013-17 |  |
| 2.13.2.1 | Relevant IHO Resolutions in M-3 | 2013-17 | no significant IHO expense anticipated |
| 2.13.3 | Develop, maintain and extend a Product Specification for the transmission of real-time surface current data | 2013-17 | no significant IHO expense anticipated |
| 2.13.4 | Develop, maintain and extend a Product Specification for dynamic surface currents in ECDIS | 2013-17 | no significant IHO expense anticipated |

## 3. 	S-100WG WORK PLAN 2015-16

Tasks

| A | Maintain and extend S-100 “IHO Universal Hydrographic Data Model” (IHO Task 2.2.2.2) |
| --- | --- |
| B | Maintain and extend S-99 “Operational Procedures for the Organization and Management of the S-100 Geospatial Information Registry” (IHO Task 2.2.2.9) |
| C | Maintain and extend the S-100 GI Registry (IHO Task 2.2.4) |
| D | [Supervise/Advise] and support the development and maintenance of S-100-based product specifications |
| E | Monitor the development of other related international standards |
| F | Provide outreach and technical assistance regarding the implementation of S-100 (IHO Task 2.2.5) |
| G | Maintain the S-100 section of the IHO website (IHO Task 2.2.2) |
| H | Conduct the 2015 and 2016 meetings of the S-100WG and its sub-group(s) and project team(s) (IHO Task 2.2.1) |

Work Items

| Work item | Title | Priority H-high M-medium L-low | Next milestone | Start Date | End Date | Status P-planned O-ongoing C-completed S-Superseded | Contact Person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Develop S-100 Edition 2.0.0 | H |  | 2010 | 2014 | C | Barrie Greenslade (UKHO) |  |  |
| A.2 | Investigate a suitable grid referencing system for S-100 | L |  | 2010 |  | P | Tony Pharaoh (IHB) |  |  |
| A.3 | Develop a guide book for using S-100 product specifications | M |  | 2010 | 2014 | C | Barrie Greenslade (UKHO)/Julia Powell (NOAA) |  |  |
| A.4 | Develop and maintain S-100 Portrayal Component | H |  | 2006 |  | C | [DIPWG] | S-100 Portrayal Register |  |
| A.5 | Develop an S-10X product specification for Auxiliary Informational Layer Integration. | M | See S-100 Edition 2.0.0 | 2010 | 2014 | C | Julia Powell (UKHO) |  |  |
| D.1 | Review the S-100 Master Plan annually | M | HSSC-7 & 8 | 2014 | Permanent | O | Barrie Greenslade (UKHO) | S-100 | Include monitoring the need to revise existing S-100-based PS (e.g. S-102) and or to develop new S-100-based PS. |
| D.2 | Review the S-101 Value Added Roadmap annually | H | HSSC-7 & 8 | 2013 | Permanent | O | Julia Powell (NOAA) | S-101 |  |
| D.2bis | Develop a template Product Specification for Marine Information Overlays (MIO) | M | HSSC-7 | 2010 | 2015 | O | Barrie Greenslade (UKHO) |  |  |
| D.3 | Develop 1st draft of S-101 ENC product specification | H |  | 2006 | 2015 | O | Julia Powell (NOAA) |  | S-100 WG to consider whether a S-101 Project Team should be established |
| D.4 | Monitor the implementation of the 1st draft of S-101 ENC product specification | H |  | 2015 |  | P |  |  |  |
| D.5 | Develop an S-100/S-101 Test Strategy and Test Bed | H |  | 2013 |  |  | Julia Powell (NOAA) |  |  |
| D.6 | Maintenance of S-101 Portrayal Component and Portrayal Catalogue | H |  |  |  |  |  | S-101 S-100 Portrayal Register |  |
| D.7 | Investigate enhancing the appearance of existing traditional paper chart symbols used in ECDIS by modifying their size, shape and colour. | L |  |  |  |  |  | S-52 S-100 Portrayal Register | DIPWG has decided to focus this effort on changes that would be implemented in S-101. If practical, these new symbols may be considered for inclusion in S-52 as well |
| D.8 | Develop Edition 2.0.0 of S-102 Bathymetric Content Specification. | H | S-102 Published April 2012 | 2014 | 2016 | P | Wade Ladner (NAVO) |  |  |
| E.1 | Monitor the development of other related international standards | M |  |  |  | P |  |  |  |
| F.1 | Liaise with IHO subsidiary bodies and subordinate organs, e.g. WWNWS-SC, NIPWG, ENCWG, etc. |  |  |  |  |  |  |  | Establish joint project teams as required |
| F.2 | Liaise with non-IHO constituents, e.g. IALA E-nav Committee, IEHC, JCOMM Expert Teams, DGIWG, ISO, marine navigation and GIS industry, etc. | H |  | 2004 | Permanent | O | Barrie Greenslade (UKHO)/Julia Powell (NOAA) |  |  |
| G.1 | Maintain the S-100 section of the IHO website | H |  | 2003 | Permanent | O | Jeff Wooton (AHS) |  |  |

Meetings (Task H)

| Date | Location | Activity |
| --- | --- | --- |
| 31 Mar-4 Apr 2014 | Sydney, Australia | TSMAD-28 / DIPWG 6 |
| 2-6 Feb 2015 (TBD) | TBD | S-100WG-1 (TSMAD-29 / DIPWG-7 tbc) |
| 2016 (TBD) | TBD | S-100WG-2 |

Chair: 	TBD	Email:

Vice Chair:	TBD	Email:

Secretary:	TBD	Email:

## 4.	SNPWG [NIPWG tbc] WORK PLAN 2015-16

Tasks

| D | Maintain Publication S-12 “Standardization of List of Lights and Fog Signals” (IHO Task 2.6.3.2) |
| --- | --- |
| E | Maintain Publication S-49 “Recommendations concerning Mariners’ Routeing Guides” (IHO Task 2.3.2.7) |
| F | Establish and monitor, in liaison with the S-100WG, the project teams required to specify and develop nautical information layers for use in ECDIS (IHO Task 2.6.2) |
| G | Develop high level specifications for a combined Marine Service Portfolio (MSP) covering the provision of hydrographic services to mariners in accordance with the IMO e-navigation strategy implementation plan |
| H | Develop a test and implementation plan for the development of the MSP “hydrographic services” |
| I | Maintain IHO Resolutions in M-3 relating to Nautical Publications as required (IHO Task 2.6.3.1) |
| J | Liaise with other HSSC WGs and other IHO and international bodies |
| K | Conduct the 2015 and 2016 meetings of the SNPWG [NIPWG tbc] and its sub-group(s) and project team(s) (IHO Tasks 2.3.1 and 2.6.1) |

Work items

| Work item | Title | Priority H-high M-medium L-low | Next Milestone | Start Date | End Date | Status P-Planned O-Ongoing C-Completed S-superseded | Contact Person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D.1 | Monitor and assess proposals for amending S-12 | M | 12/2014 | 2014 | Permanent |  |  | S-12 | In close liaison with IALA; see J.4 |
| F.1 | Assess the progress and perspectives of developing specifications for NP data layers in ECDIS and propose the way forward for consideration by HSSC | H |  |  |  |  |  |  | To be considered in the context of the IMO e-navigation strategy implementation plan (subject to the outcome of NCSR 1). [NIPWG] to consider establishing one or more project team(s) in liaison with S-100WG as required (see J.2), in particular to continue the development of Product Specifications currently assigned to the SNPWG. |
| F.2 | Investigate the interaction between Marine Protected Area Product and ENC in ECDIS | M |  | 2015 | Permanent |  | Chair/Sec |  | In close liaison with the S-100 WG (if founded) or TSMAD |
| F.3 | Model the NP data where required. | H |  | 2004 | Permanent | O | Chair/Sec |  | S-100 related. To be included in NPUBS domain of the FCD Register |
| F.4 | Review of objects and attributes | H | 12/2014 | 2004 | Permanent | O | Chair/Sec |  | S-100 related. According to the tasks assigned by HSSC4 |
| F.5 | Propose amendments to HYDRO domain of the FCD Register | H |  | 2005 | Permanent | O | Chair/Sec |  | S-100 related. To be included in the FCD register |
| F.6 | Propose amendments to AtoN domain of the FCD Register | H | 08/2014 | 2014 | 2014 | O | Chair/Sec | S-125 | To improve the current definitions and attribute values at the FCD register |
| F.7 | Populate the NPUBS domain of the FCD Register | H |  | 2006 | Permanent | O | Chair/Sec |  | S-100 related. Awaiting Registry improvements |
| F.8.1 | Develop S-12n - Nautical Information Product Specification |  |  |  |  |  |  |  | Liaise with WWNWS-Sub committee |
| F.8.1.1 | For Radio Services | H | 12/2014 | 2012 | 2016 | O | Chair/Sec | S-123 |  |
| F.8.1.2 | For Navigational services | H | 12/2014 | 2013 | 2016 | O | Chair/Sec | S-125 |  |
| F.8.1.3 | For Traffic management | H | 12/2014 | 2013 | 2016 | O | Chair/Sec | S-127 |  |
| F.8.1.3.1 | For Marine Protected Areas | H | 12/2014 | 2011 | 2015 | O | Chair/Sec | S-122 | Awaiting completion of S-100 Edition 2 and Feature Catalogue Builder |
| F.8.1.4 | For Physical environment | H | 12/2014 | 2013 | 2016 | O | Chair/Sec | S-126 |  |
| G.1 | Monitor the requirements for and provision of nautical information in e-navigation test-beds Produce NP1 sample data sets | M |  |  |  |  |  |  | According to the tasks assigned by HSSC4. Collection of information to be modelled |
| G.1.1 | For Radio Services | H | 12/2014 | 2012 | 2014 | O | Chair/Sec | S-123 |  |
| G.1.2 | For Navigational services | H | 12/2014 | 2012 | 2015 | O | Chair/Sec | S-125 |  |
| G.1.3 | For Traffic management | H | 12/2014 | 2012 | 2015 | O | Chair/Sec | S-127 | Marine Protected Area Part was completed in 2012 |
| G.1.4 | For Physical environment | H | 12/2014 | 2013 | 2015 | O | Chair/Sec | S-126 |  |
| G.2 | Set up a test bed ECDIS | M |  | - | - | P | Chair/Sec |  |  |
| G.3 | Rules and guidelines for displaying nautical information in ECDIS and in combined Marine Service Portfolios |  |  |  |  |  |  |  |  |
| G.3.1 | Develop basic display rules for NP data intended for use in ECDIS (NP3) | M |  | 2008 | 2015* | O | Chair/Sec | S-52 | Close co-operation with [DIPWG] required *end date depends on [DIPWG] schedule |
| G.3.2 | Develop guidelines showing how navigation information received by communications equipment can be displayed in a harmonised way and what equipment functionality is necessary. | M |  | 2015 | 2019 | P |  | S-52 | Draft e-nav IMO Strategy Implementation Plan, Task T13 (HSSC6-07.1A refers). |
| G.4 | Initiate consideration of the architecture of the MSP “hydrographic services” | M |  | 2013 |  | P | Chair [NIPWG] |  | To be considered in the context of the IMO e-navigation strategy implementation plan (subject to the outcome of MSC 94) Draft e-nav IMO Strategy Implementation Plan, Task T17 (HSSC6-07.1A refers). |
| G.5 | Contribute to considering the future of paper charts in the perspective of the establishment of MSPs | M |  | 2014 |  |  |  |  |  |
| I.1 | Maintain and extend resolutions in M-3 relating to Nautical Publications | M | 12/2014 | 2012 | Permanent | O | Chair/Sec [NIPWG] | M-3 | A review is scheduled due to harmonization of M3 information and potential ProdSpecs content |
| J.0 | Liaise with the CSPCWG |  |  |  | Permanent until step2 | O | Chair/Sec NIPWG |  | Establish joint project teams as required |
| J.1 | Liaise with the ENCWG | H |  |  | Permanent | O | Chair/Sec [NIPWG] |  |  |
| J.2 | Liaise with the S-100WG | H |  |  | Permanent | O | Chair/Sec [NIPWG] |  | Establish joint project teams as required |
| J.2.1 | Draft Data Capture and Encoding Guides |  |  |  |  |  |  |  | Document for NPs similar to Use of the Object Catalogue |
| J.2.1.1 | For Marine Protected Areas | H | 12/2014 | 2011 | 2015 | O | Chair/Sec | S-122 | To be harmonized with S-101 DCEG; Awaiting next S-100 version |
| J.2.1.2 | For Radio Services | M |  | 2015 | 2015 | P | Chair/Sec | S-123 | Depends on modelling progress |
| J.2.3 | Draft Product Specification |  |  |  |  |  |  |  |  |
| J.2.3.1 | For Radio Services | H | 12/2014 | 2014 | 2015 | O | Chair/Sec | S-123 |  |
| J.2.3.2 | For Navigational services | H | 12/2014 | - | - | P | Chair/Sec | S-125 |  |
| J.2.3.3 | For Traffic management | H | 12/2014 | 2011 | 2016 | O | Chair/Sec | S-127 | The start date is in-line with the MPA ProdSpec development |
| J.2.3.4 | For Marine Protected Areas | H | 12/2014 | 2011 | 2015 | O | Chair/Sec | S-122 | Depends on progress of next S-100 version allowing GML data use |
| J.2.3.5 | For Physical environment | H | 12/2014 | - | - | P | Chair/Sec | S-126 |  |
| J.3 | Liaise with other HSSC WG | H |  | 2004 | Permanent | O | Chair/Sec [NIPWG] |  | Including DPSWG, DQWG, TWCWG, etc. |
| J.4 | Liaise with IALA e-Nav Committee | H |  | 2013 | Permanent | O | Chair/Sec [NIPWG] |  | As advised by HSSC4 (in liaison with S-100WG). |

Meetings (Task K)

| Date | Location | Activity |
| --- | --- | --- |
| 7-11 Apr 2014 | Rostock, Germany | SNPWG 17 |
| 1-4 Dec 2014 | Cadiz, Spain | SNPWG 18 |
| 2015 (TBD) | TBD | SNPWG 19 [NIPWG-1] |
| 2016 (TBD) | TBD | NIPWG-2 |

Chair: TBD	Email:
 Vice Chair: TBD	Email:
 Secretary: TBD	Email:

## 5.	ENCWG WORK PLAN 2015-16

Tasks

| A | Maintain S-52 “Specifications for Chart Content and Display Aspects of ECDIS” and its associated “Presentation Library” (IHO Task 2.3.2) |
| --- | --- |
| B | Maintain S-57 “IHO Transfer Standard for Digital Hydrographic Data” (IHO Task 2.2.2) |
| C | Maintain S-58 “Recommended ENC validation checks” (IHO Task 2.2.2) |
| D | Maintain S-61 “Product Specification for Raster Navigational Charts” (IHO Task 2.2.2) |
| E | Maintain S-64 “IHO Test Data Sets for ECDIS” (IHO Task 2.2.2) |
| F | Maintain S-65 “ENC Production, Maintenance and Distribution Guidance” (IHO Task 2.2.2) |
| G | Assess the impact of other IHO standards on S-52 display specifications |
| H | Liaise with the NIPWG (IHO Task 2.3.2) |
| I | Maintain the ENC production and portrayal sections of the IHO website (IHO Task 2.2.2 & 2.3.2) |
| J | Conduct the 2015 and 2016 meetings of ENCWG and its sub-group(s) and project team(s) (IHO Task 2.2.1) |

Work items

| Work item | Title | Priority H-high M-medium L-low | Next milestone | Start Date | End Date | Status P-planned O-ongoing C-completed S-Superseded | Contact Person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Resolve any problems or errors identified in the current editions of S-52 and its Presentation Library | H |  | 2009 | Permanent | O | Colby Harmon Tom Mellor | S-52 |  |
| B.1 | Resolve any problems or errors identified in the current edition of S-57 | H |  | 2011 |  | O |  |  |  |
| B.2 | Study the possibility to encode information features as New Objects (see S-57 supplement) to avoid caution area objects (CNTARE) in some cases, e.g. to encode T&Ps” | M |  | 2014 | 2015 | O | Richard Fowle (IC-ENC) |  |  |
| C.1 | Monitor the implementation of the new edition of S-58 and keep the recommended checks up to date | H |  | 2003 |  | O | Richard Fowle (UKHO) |  |  |
| C.2 | Resolve any problems or errors identified in the current edition of S-58 | H |  | 2003 | Permanent | O | Richard Fowle (UKHO) |  |  |
| C.3 | 1. Restructure S-58 to provide a more logical means of data validation. 2. Investigate how the new version of S-58 can be used to implement a minimum validation standard for all ENCs. | H | Edition 5.0.0 June 2014 | 2012 | 2014 | C | Richard Fowle (IC-ENC) |  |  |
| E.1 | Resolve any problems or errors identified in the current edition of S-64 | H |  |  |  |  |  |  |  |
| E.2 | Investigate expanding S-64 to improve its usefulness for both OEMs and type approval authorities | H | Edition 4.0.0 | 2012 | 2014 | C | Tom Richardson/Tom Mellor (UKHO) |  |  |
| F.1 | Monitor and assess proposals for amending S-65 | L |  |  | Permanent | O |  |  |  |
| H.1 | Liaise with the NIPWG | H |  |  |  |  |  |  |  |
| I.1 | Maintain the ENC production and portrayal sections of the IHO website, and support FAQ and Encoding Bulletins | H |  | 2003 | Permanent | O | Jeff Wooton (AHS) Barrie Greenslade Colby Harmon IHB ADCS |  | Include posting EBs and PBs |

Meetings (Task J)

| Date | Location | Activity |
| --- | --- | --- |
| 31 Mar-4 Apr 2014 | Sydney, Australia | TSMAD-28 & DIPWG-6 |
| 2-6 Feb 2015 (TBD) | TBD | ENCWG-1 (TSMAD-29 / DIPWG-7 tbc) |
| 2016 (TBD) | TBD | ENCWG-2 |

Chair: TBD	Email:
Vice Chair: TBD	Email:
Secretary: TBD	Email:

## 6.	DPSWG WORK PLAN 2015-16

Draft in preparation.

For the record: Decision to be made on the extension of S-63 digital signatures beyond ENC (HSSC6-05.2B refers).

## 7.	TWCWG [TWLWG + SCWG tbc] WORK PLAN 2015-16

Tasks

| A | Maintain the list of standard tidal constituents (IHO Task 2.7.2.3) |
| --- | --- |
| B | Develop and maintain a standard for digital tide tables (IHO Task 2.7.3) |
| C | Prepare and maintain an inventory of tide gauges used by Member States and publish it on the IHO/TWLWG web site (IHO Task 2.7.2.4) |
| D | Compare the tidal predictions generated as a result of analysis of a common data set using different analysis software |
| E | Review feedback of on-line real time water level observation document |
| F | Develop and maintain a standard for the transmission of real-time tidal data (IHO Task 2.7.4) |
| G | Develop and maintain a product specification for the transmission of real-time surface current data (S-111 - IHO Task 2.13.3) |
| H | Develop and maintain a product specification for dynamic application of navigationally significant surface currents in ECDIS (IHO Task 2.13.4) |
| I | Develop and maintain a product specification for dynamic application of tides in ECDIS (IHO Task 2.7.5) |
| J | Liaise with industry experts on the development of product specifications for tides and currents (IHO Tasks 2.7.2 and 2.13.2) |
| K | Liaise with S-100WG on tidal and current matters relevant to ECDIS and GIS applications (IHO Tasks 2.7.4, 2.7.5, 2.13.3 and 2.13.4) |
| L | Maintain IHO Resolutions in M-3 relating to tides, water levels and currents as required (IHO Tasks 2.7.2.1 and 2.13.2.1) |
| M | Develop and maintain material for course on tides and tidal streams |
| N | Conduct the 2015 and 2016 meetings of TWCWG and its sub-group(s) and project team(s) (IHO Tasks 2.7.1 and 2.13.1) |

Work items

| Work item | Title | Priority H-high M-medium L-low | Next milestone | Start Date | End Date | Status P-planned O-ongoing C-completed S-Superseded | Contact Person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Maintain the list of standard tidal constituents | H | Review current list of published tidal constituents | - | Permanent | O | Chris Jones* |  |  |
| B.2 | Prepare a Standard for Digital Tide Tables | H | Prepare draft Standard | 2009 | 2015 | O | Stephen Gill* Chris Jones Zarina Jayaswal |  |  |
| C.1 | Prepare and maintain an inventory of tide gauges used by Member States and publish it on the IHO/TWCWG web site. | H |  | - | Permanent | O | David Wyatt* All |  | Initial inventory from TWCWG members available on IHO web site. |
| D.1 | Compare the tidal predictions generated as a result of analysis of a common data set using different analysis software. | H |  |  |  | O | Stephen Gill* All |  | Select Common data set Analyze using different software Predict common set of tides Compare results |
| D.2 | The study of long term data sets for the determination of global sea level rise. | H |  |  | Permanent | O | Stephen Gill* All |  |  |
| F.1 | Develop and maintain a standard for the transmission of real-time tidal data | H |  | 2009 | 2015 | O | Chris Jones* All |  | Liaise with S-100WG (see K.1) |
| G.1 | Develop and maintain a product specification for the transmission of real-time surface current data (S-111) | H | Include section on real-time data in the PS Liaise with TWLWG on standards and methods | 2014 2014 | 2017 2017 | O O | Maltais*, Kammerer Hess*, Jan, Pronost |  | Liaise with S-100WG (see K.1) |
| G.2 | Establish formats for the transmission and display of real-time current data | H | Prepare test data sets for transmission Test the portrayal of real-time current data | 2014 2014 | 2017 2017 | O | Kammerer*, Maltais Weaver*, Sullivan, Kammerer |  |  |
| H.1 | Develop and maintain a product specification for dynamic application of navigationally significant surface currents in ECDIS | H | Develop and review the initial outline of the PS Revise initial outline of PS Develop initial draft of PS that includes portrayal, schema, and encoding | 2013 2013 2014 | 2014 2014 2015 | C O O | Maltais*, All Maltais*, All Maltais*,Sullivan, Hess, Mong, All |  | Liaise with S-100WG (see K.1) |
| H.2 | Establish formats for the transmission and display of data from historical observations, astronomical predictions, and forecasts of total surface current | M | Prepare test data sets for transmission Test the portrayal of surface current vectors |  |  |  | Kammerer*, Maltais, Pronost, Kuilman, Byun Weaver*, Opdyke, Sullivan, Kammerer |  |  |
| I.1 | Develop and maintain a product specification for dynamic application of tides in ECDIS | H H | Prepare draft Product Specifications (S-1**) for tidal data in S-100. Prepare draft portrayal model for tidal data in S-100. | 2010 2012 | 2015 2015 | O O | Zarina Jayaswal* Glen Rowe Bill Mitchell Kwang-nam Han Stephen Gill* Bill Mitchell Zarina Jayaswal |  | Liaise with S-100WG (see K.1) S-100, S-102 |
| J.1 | Liaise with industry experts on the development of product specifications for tides and currents | M | Contact appropriate product developers Receive feedback on the specifics of portrayal and data transmission Revise standards according to feasibility | 2014 2014 2014 | 2017 2017 2017 | O O P | All Hess*, Sullivan, Kammerer, Weaver, Opdyke Maltais*, Hess, Weaver, Sullivan, Anderson, All |  |  |
| K.1 | Liaise with S-100WG on tidal and current matters relevant to ECDIS applications | H |  |  |  | O | Gwenaële Jan Kurt Hess |  | Establish joint project teams as required. |
| K.2 | Liaise with TSMAD, DIPWG and TWLWG on surface current matters relevant to the Dynamic Application of Surface Currents in ECDIS | H | Prepare and discuss scoping and technical requirements Prepare Product Specification (S111) for surface current data in S-100 for review and acceptance | 2013 2014 | 2014 2016 | O P | Hess*, All Hess*, All |  |  |
| L.1 | Relevant IHO Resolutions in M-3 | H | Keep the Resolutions fit for purpose |  | Permanent | O |  |  |  |
| L.2 | S-60 User´s Handbook on Datum Transformations involving WGS 84 | M |  |  | Permanent | O |  |  |  |
| L.3 | Review the various definitions of MSL and their relevance to Hydrographic Offices and review the IHO tidal resolutions to ensure that they are compatible with the requirements of non-tidal areas such as the Baltic Sea. | H H | IHO Resolution 3/1919, as amended, approved by HSSC 5. Required reviewed of definitions of MSL and LAT for submission to HDWG Review wording of IHO Resolution 3/1919, as amended, in light of revised definitions for MSL and LAT | 2009 2014 | 2014 2015 | C O |  |  | IHO Resolution 3/1919 as amended |
| M.1 | Develop and maintain material for course on tides and tidal streams | H | Adapt currently available course material to create a course suitable for delivery in support of CBSC requests. | 2013 | 2015 | O | Stephen Gill* Bill Mitchell Ruth Farre |  |  |

Meetings (Task N)

| Date | Location | Activity |
| --- | --- | --- |
| 25-28 Mar 2014 | Wollongong, Australia | TWLWG-6 |
| 3-5 Jun 2014 | Quebec City, Canada | SCWG-2 |
| 21-24 Apr + 13-15 May 2015 | Silver Spring, US + Tokyo, Japan | TWCWG-1 = TWLWG7 + SCWG3 |
| 2016 (TBD) | TBD | TWCWG-2 |

Chair: TBD	Email:
Vice Chair: TBD	Email:
Secretary: TBD	Email:

8.	CSPCWG WORK PLAN 2015-16

Tasks

| A | Maintain and extend Publication S-4 'Chart Specifications of the IHO & Regulations of the IHO for INT Charts' (IHO Task 2.3.2) |
| --- | --- |
| B | Maintain and extend Publication S-11 Part A „Guidance for the Preparation and Maintenance of INT Chart schemes‟ (IHO Task 2.3.2) |
| D | Development of new (and revised) symbology (IHO Task 2.3.2) |
| E | Maintenance of S-4 supplementary publications INT 1, 2 & 3 (IHO Task 2.3.2) |
| F | Maintain and extend Publication S-49 'Recommendations concerning Mariners' Routeing Guides' (IHO Task 2.3.2) |
| G | Conduct annual meetings of CSPCWG (IHO Task 2.3.1) |

Work items

| Work item | Title | Priority H-high M-medium L-low | Next Milestone | Start Date | End Date | Status P-Planned O-Ongoing C-Completed S-superseded | Contact Person(s) | Affected Pubs/Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.6 | Revise S-4 Part B Section 500 | M | Publish S-4 Ed 4.5.0 | 2012 | 2014 | O | Sec CSPCWG | S-4 / B-500 | CL 69/2014 |
| A.11 | Clarify guidance on dredged/maintained areas | M | WG letter with draft specification | 2011 | 2015 | O | Sec CSPCWG | S-4, INT1 | CSPCWG9 Action 43 CSPCWG10 Action 10 |
| A13 | Provide guidance on charting maximum authorized draught | M | WG letter with draft specification | 2012 | 2015 | O | Sec CSPCWG | S-4, INT1 | Draft guidance approved by WG but on hold pending development of symbol, D34 refers. |
| A14 | Provide guidance on updating large scale charts first | M | Publish S-4 Ed.4.5.0 | 2012 | 2014 | O | Sec CSPCWG | S-4 / B-100.5 | CL 69/2014 |
| A16 | Initiate consideration of the „future of the paper chart‟ | M | Discussion paper by AU / CA / SE CSPCWG reps | 2014 |  | P O | Chair CSPCWG | tbd | CSPCWG10 Action 36 |
| A17 | Provide guidance on charting wind farms under construction at sea | M | WG letter with draft specification | 2014 | 2015 | O | Sec CSPCWG | S-4 B-445 | CSPCWG10 Action 20 |
| A18 | Provide guidance on charting covered berths | M | WG letter with draft specification | 2014 | 2015 | O | Sec CSPCWG | S-4 B-300 | CSPCWG10 Action 21 |
| A19 | Provide additional guidance on charting AIS where on most AtoN in region | M | WG letter with draft specification | 2014 | 2015 | O | Sec CSPCWG | S-4 B-489 | CSPCWG10 Action 28 |
| A20 | Provide guidance on use of QR codes | M | WG letter with draft specification | 2014 | 2015 | O | Sec CSPCWG | S-4 B-200? | CSPCWG10 Action 38 |
| A21 | Provide guidance on adding reminder about T & P NMs on charts | M | WG letter with draft specification | 2014 | 2015 | O | Sec CSPCWG | S-4 B-200? | CSPCWG10 Action 41 |
| B.3 | Develop guidelines for preparation & maintenance of small / medium scale ENC schemes. | H | 2nd draft by NSEHWG | 2009 | 2014 | O | Vice Chair CSPCWG | S-11A | Draft by NSEHWG; keep WENDWG engaged |
| D32.1 | Lights issues: Major lights, Direction lights, Highlighting | M | Publish S-4 Ed 4.5.0 | 2012 | 2014 | O | Sec CSPCWG | S-4 / B-470 | CL 69/2014 |
| D32.2 | Interrupted lights | M | Publish S-4 Ed 4.5.0 | 2012 | 2015 | O | Sec CSPCWG | S-4 / B-470 | CSPCWG9 Action 13 CSPCWG10 Action 22,23 |
| D32.4 | Reinstate (simplified) symbol for light vessels | M | CL for MS approval | 2012 | 20153 | O | Sec CSPCWG | S-4 / B-474, INT1 | CSPCWG9 Action 18; CSPCWG10 Action 16 |
| D34 | Devise new symbol for ‘Maximum authorized draught’ | M | Draft to WG | 2014 | 2015 | P | Sec CSPCWG | S-4 / B-400 | CSPCWG10 Action 12; see also A13. |
| D35 | Dangerous cargo berth | M | WG letter with draft specification | 2014 | 2015 | P | Sec CSPCWG | S4 / B-300 | CSPCWG10 Action 18 |
| E.1 | Maintain official INT 1s |  | Planning for next editions by INT1 sub- WG (following Cadiz meeting July 2013) | 2013 | 2015? | O | DE: S Spohn FR: S Guillou ES: A Guitart | INT 1 | English version 2011 (Ed 7) French version 2012 (Ed 5) Spanish version 2011 (Ed 4) |
| E.4 | Symbols for vacant entries in INT 1 | L |  | 2014 |  | P | Sec CSPCWG | INT 1, S-4 part B | Consider subsuming into E8 Not subsumed |
| E8 | Reorganize INT1 to exclude composite symbols | L | Next round of NEs of INT1? Discuss at WG10 (11.2) | 2013 | 2015? | O P | INT1 sub-WG | INT1 | Not to be progressed at present; use CSPCWG10-11.2A when progressed. |
| E9 | Develop new section V for INT1 for ‘data quality’ | M | Draft to WG | 2014 | 2016 | O | Chair CSPCWG | INT1 | CSPCWG10 Action 35 |

Meetings (Task G)

| Date | Location | Activity |
| --- | --- | --- |
| 21-24 Jan 2014 | Wellington, New Zealand | CSPCWG 10 |
| 28-30 April 2015 | Rostock, Germany | CSPCWG 11 |

Chairman: Peter Jones (UK) until 31/03/14		Email: 	peter.jones@ukho.gov.uk 
Chairman: Jeff Wootton (AU) from 01/04/14 		Email:	jeff.wootton@defence.gov.au
Vice Chairman: Jeff Wootton (AU) until 31/03/14	Email:	jeff.wootton@defence.gov.au 
Vice Chairman: Chris Thorne (UK) from 01/04/14	Email: 	chris.thorne@ukho.gov.uk
Vice Chairman: Nick Webb (UK) from 01/09/14	Email:	nick.webb@ukho.gov.uk
Secretary: Andrew Heath-Coleman (UK)		Email:	andrew.coleman@ukho.gov.uk

9.	DQWG WORK PLAN 2015-16

Tasks

| A | Review ISO 19113, Geographic Information-Quality Principles, ISO 19114, Geographic Information-Quality Evaluation Procedures, and ISO 19115, Geographic Information - Metadata and propose relevant enhancements and amendments for incorporation in S-100 “IHO Universal Hydrographic Data Model” (IHO Task 2.5.2) |
| --- | --- |
| B | Monitor and further develop quality indicators for hydrographic data (IHO Task 2.5.2) |
| C | Maintain and extend as needed existing quality indicators in S-57 “IHO Transfer Standard for Digital Hydrographic Data”, including the education of both the mariner and the cartographer, and the development of documentation (IHO Task 2.5.2) |
| D | Maintain and extend as needed the presentation of data quality, as provided in S-52 “Specifications for Chart Content and Display Aspects of ECDIS” and its Presentation Library (IHO Task 2.5.2) |
| E | Investigate ways of ensuring that ECDIS displays provide a clear warning or indication to the mariner on the quality of the underlying survey data, through appropriate use of the attribute CATZOC and/or improvement of the existing display capabilities (IHO Task 2.5.2) |
| F | Propose new data quality topics and other applications for consideration by HSSC (IHO Task 2.5.2) |
| G | Maintain and extend data quality related elements of S-100 “IHO Universal Hydrographic Data Model” (IHO Task 2.5.2) |
| H | Maintain and extend data quality related elements of S-101 “ENC Product Specification” and other S-100-based Product Specifications (IHO Task 2.5.2) |
| I | Conduct the annual meetings of DQWG (IHO Task 2.5.1) |

Work items

| Work Item | Title | Priority H-High M-Medium L-Low | Next Milestone | Start Date | End Date | Status P-Planned O-Ongoing C-Completed S-superseded | Contact Person(s) | Related Pubs / Standards | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Review ISO 19113, 19114, 19115 and 19157 and make recommendations for inclusion in S-100 | M |  | 2010 | Permanent | O | CSPCWG | S-100 | Ongoing task to keep S-100 data quality in line with ISO standards. |
| B.4 | Develop the hierarchy approach by formalizing the hierarchy and the algorithm that drive the display | H | TSMAD29 ? | 2013 | 2015 ? | O | Mike Prince | S-101 | To be completed for submission to TSMAD29 ?. |
| C.4 | Investigate possible methods for how to educate practicing mariners on data quality issues. | H | DQWG9 | 2010 | 2015 | O | DQWG |  | Investigate in liaison with training institutions the adequacy of existing HOs‟ documentation on the quality aspects of the practical use of ENCs. IHO CL 51/2013 issued on this topic. To include the recommendations of HSSC5-INF4, interface with IMO/HTW (Action HSSC5/45 refers). |
| E.1 | Develop logic for indicators in current and proposed approaches. | H | DQWG9 | 2010 | 2014 | O | Mike Prince | - | To be completed for submission to TSMAD29 ?. |
| E.2 | Demonstrate methods to mariners. | H | Follows S-100 demonstrator | 2012 | 2014 | O | DQWG | S-101 | Build possible methods into ENC and ECDIS to demonstrate effectiveness. |
| E.3 | Demonstrate methods to mariners | H | Follows E.1 | 2014 | 2015 | P | C Howlett |  | Consider using the Singapore Strait Marine Electronic Highways (MEH) project as a test case (Action HSSC5/47 refers). |
| F.1 | Investigate areas of quality concern (other than survey / bathymetry) | M | DQWG9 | 2010 | Permanent | O | Eivind Mong | - | SNPWG has responded, liaison is ongoing. |
| H.1 | Establish contact with other working groups to investigate scope of data quality items for the S-10x standards (e.g. TSMAD for S-102) | M |  | - | - | P |  |  | To specifically seek contact and collaboration with the TWLWG to include data quality elements into dynamic tide / water levels (Action HSSC5/46 refers). |

Meetings (Task I)

| Date | Location | Activity |
| --- | --- | --- |
| 25-27 Mar 2014 | Wollongong, Australia | DQWG 8 |
| 5-7 Nov 2014 | Poole, UK | DQWG 9 |
| -- 2015 | -- | -- |

Chair: Chris HOWLETT, UK                                     Email: Chris.Howlett@ukho.gov.uk

Vice-Chair: Antti Castren, Finland		    Email: antti.castren@fta.fi 
Secretary: Eivind MONG, Jeppesen                              Email: Eivind.Mong@jeppesen.com

10.	MSDIWG WORK PLAN 2015-16

Tasks

| A | Identify and promote national and regional best practices: - for land-sea integration - for cross-border integration |
| --- | --- |
| B | Review the appropriateness of existing standards for the provision of the maritime components of spatial data infrastructures |
| C | Develop content for an MSDI training course |
| D | Maintain MSDI reference documentation on the IHO website |
| E | Maintain and extend Publication IHO MSDI C-17 (IHO Task 2.9.2 refers) |
| F | Conduct annual meetings of MSDIWG, arranged back to back with 1-day MSDI Open Forum (IHO Task 2.9.1 refers) |
| G | Ensure that MSDI is a standing agenda item for RHCs’ meetings (IHO Res 2/1997, as amended, refers) |

Work items

| Ref | Task | Activities | Priority H-high M-med L-low | Actions | Start Date | End Date | Status P-planned O-ongoing C-completed | Responsible / contact person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Identify and promote national and regional best practices: | To consider the impact of the UN- GGIM initiative, taking into account the items identified in paragraph 11 of HSSC5-05.7B | H | Land-sea integration Cross-border integration | Mar 2014 | 2016 | P | GeoSci (Aus), DK, FR, JP, SP, US | GGIM -3. UNITED NATIONS E/C.20/2013/10/Add.1 | http://ggim.un.org/ggim_committee.html |
| A.1 |  | Create relevant use cases, from potential users of MSDI | H | 1.1.Provide examples of generic providers of relevant data 1.2 Provide examples about user requirements | Jun 2014 | Feb 2015 | P | GeoSci (Aus), DK, FR, JP, SP, US |  | Report to MSDIWG-6 |
| A.2 |  | Set up a survey to establish current position in respect of benefits and challenges faced by MS’s role in NSDI and/ or MSDI | M | 2.1. Prepare questionnaire to investigate challenges and benefits in relation to MSDI 2.2.Circulate questionnaire to MS 2.3 Analyse results and use to update C-17 and on-line resources (Ref:Task D) | Apr 2014 May 2014 July 2014 | May 2015 June 2015 Aug 2015 | P | GeoSci (Aus), DK, FR, JP, SP, US |  | Report to HSSC-6.Nov 2014 |
| A.3 |  | Monitor and report on national, regional and international MSDI activities and report to enable increased visibility of hydrographic importance | H | 3.1 Identify relevant initiatives 3.2 Engage with relevant initiatives | Apr 2014 | Feb 2018 | O | GeoSci (Aus), DK, FR, JP, SP, US |  | Report to MSDIWG-6 |
| B/B.1 | Review the appropriateness of existing standards for the provision of the maritime components of spatial data infrastructures | Liaise with TSMAD regarding level of S-100 understanding and use in support of SDI activities (e.g. INSPIRE) | H | B.1.1 Identify new S-1XX data specifications for datasets in MSDI B.1.2 Determine and log any issues of concern in WG regarding new standards and obtain feedback from TSMAD on them | Feb 2014 Feb 2014 | Feb 2018 | O | NL, NO, UK Caris,Envitia, | INSPIRE, Draft EC Directive on MSP and ICM | Report to MSDIWG-6 |
| C C.1 | Develop content for MSDI training course(s) Identify the need for education and training among the Member States and report to WG Chair C.1.1 Develop and deliver training and education events as required C.1.2 Investigate the possibilities to arrange an IHO INSPIRE Workshop with EC-JRC | Determine which HOs in Europe (via Poll) are interested to have training involving EC-JRC (INSPIRE) & DG MARE (MSP Directive) Harness the relationship between IHO and JRC Gain greater working understanding/knowledge of EC INSPIRE and Marine Data Governance | H H | Prepare a short paper and questionnaire for IHB to send out to the EC MS. Assuming positive response, produce a programme 1.5 day workshop arranged by IHB | Mar 2014 Mar 2014 Mar 2014 | Jan 2018 Feb 2015 July 2014 | O O O | Esri, USA, OceanWise |  | Report to MSDIWG-6 |
| C.2 | Establish a MSDI training syllabus for use across IHO community aimed at: Senior Managers (i.e. Directors, Hydrographers, HR Managers); Practitioners (i.e. Hydrographic Surveyors, Cartographers, Oceanographers, IT specialists) | C.2.1 Develop topic areas (vice syllabus) for various levels: C.2.2 Prepare proposal for IHB on Website On-line training resource capability C.2.3 Provide input to IHB for the design and development of the Website for virtual training | H M M | Senior Managers (1 day) Middle Managers (2 day) Tech Staff (5 day) To include provision of training opportunities, short training sessions, links with on-line resources, case studies, technical reports) Link to Task D.1.3 | Mar 2014 May 2014 Oct 2014 | Oct 2014 Aug 2014 Feb 2015 | O O P | Esri, USA, OceanWise Esri, USA, OceanWise Esri, USA, OceanWise | IHO Pub: C-17 |  |
| D/D.1 | Maintain MSDI reference documentation on the IHO website | D.1.1 Prepare a proposal to MSDIWG on re-structuring the MSDIWG page on the IHO website. D.1.2 Request relevant MSDI information from IHO Member States. D.1.3 Collect education information relating to MSDI, in coordination with sub-group C. | H H M | Deliver to MSDIWG6 CL sending questionnaire On Completion of task C.2. | June 2014 Oct 2013 Oct 2014 | Feb 2015 Feb 2015 Feb 2015 | P P P | Esri,IHB,DK |  |  |
| E E.1 | Maintain and extend Publication IHO MSDI C-17 (IHO Task 2.9.2 refers) Conduct a review of MSDI that includes conceptual descriptions of the four sub-areas of MSDI as | E.1.1 Technical issues E.1.2 Governance E.1.3 Standards and specifications E.1.4 Content (data) | H H | Review C-17 for updating/ restructuring/additions/modernizing Alignment with OGC Provide changes as a result of the MS survey in Task A Update information Provide case studies – see Task A Best practice guidelines defined – see Task A Define publishing mechanism for sharing data Ref Task A: Assist with questionnaire development for MS survey based on the review of C-17 Ref Task A: Update C-17 Annex A, SDI References (consider using survey to assist in update) | Mar 2014 Mar 2014 | Oct 2015 Feb 2015 | P P | GeoSci (Aus), USA, FR, NL, RO | CBSC MSDI Syllabus, INSPIRE, OGC, ISO, IHO, RHC reports, MSDIWG MS inputs | Discuss and review survey results at MSDIWG6 to determine next steps |
| E.2 | Monitor technical developments in relation to MSDI | E.2.1.Review GGIM and OGC Oil Spill Results for relevance to C-17 E.2.2 Chair to request WG Members to notify twice yearly about developments that have occurred or are coming that may affect MSDI and/or C-17 | H | Define the scope of the work related to interoperability Monitor developments Provide status report to MSDIWG including recommendations on how to proceed Standing WG Agenda item | Jun 2014 | Feb 2018 | P | GeoSci (Aust), USA, FR, NL, RO | TSMAD |  |
| E.3 | Determine hydrographic data set(s) that should be included in MSDI | E.3.1 Prepare MS survey questionnaire based on WG responses (Top 10 list), requesting MS to prioritize and add any new ones E.3.2 Publish priority list of top data layers on IHO Website | H | Prioritize data layers by usefulness to non- navigational sectors Identify priority order of importance (High, medium, low) Identify “core” reference datasets for MSDI Establish top 10 list Define publishing mechanism for sharing data | Mar 2014 | Feb 2015 | P | Geo-Sci (Aus), USA, FR, NL, RO |  |  |
| F F.1 | Conduct annual meetings of MSDIWG, arranged back to back with 1-day MSDI Open Forum (IHO Task 2.9.1 refers) Organise Open Forum and MSDIWG6 | F.1.1.Identify HO to host WG6 and Open Forum F.1.2 Form task team to develop content for Open Forum 2015 F.1.3 Arrange MSDIWG Agenda, Workshop programme and task group topics | H H H | Confirm venue, dates and agenda, logistics Plan programme and topic areas, Invite speakers and stakeholders Review Action Plan and report Develop agenda and circulate | Sept 2013 Mar 2014 July 2014 Sept 2014 Nov 2014 | Feb 2018 June 2014 Sept 2014 Oct 2014 Nov 2014 | O O O O O | UK, Esri, OceanWise, IHB Chair, Vice-Chair and Secretary |  | UKHO to host |
| G G.1 G.2 | Ensure that MSDI is a standing agenda item for RHCs’ meetings (IHO Res 2/1997 as amended) Provide position paper to IRCC 2014 on MSDI and its importance to IHO Coordinate and collate all MSDI inputs and actions from RHC’s to MSDIWG | G.1.1.First draft for circulation G.1.2 Include comments and prepare final version G.1.3 Present to IRCC 2014 on the value and benefit to be derived by HO from MSDI G.1.4 Provide a discussion paper on the role of HO’s in the provision of e-navigation services G.2.1. MSDIWG to appoint a coordinator to collate MSDI status reports from RHC’s G.2.2.Coordinator to ensure status reports feed into MSDIWG review of current practise | H H H H H H H | Circulated to HSSC Chair for comment by end March Submit to IRCC secretary Aim is to reinforce the need for all RHC’s to place MSDI as a standing agenda item Reinforcement of importance of MSDI as an enabler to e-Navigation Coordinator appointed All reports delivered and collated as inputs to MSDIWG Action Plan | Feb 2014 Mar 2014 Apr 2014 May 2014 Mar 2014 June 2014 April 2014 | Feb 2018 March 2014 Apr 2014 May 2014 Apr 2014 May 2018 2018 | O C C C O P P | UKHO, Esri OceanWise | Hydro Int Feb 2014 article by M. Bergmann | HSSC, IRCC, CBSC |

Meetings (Task F)

| Date | Location | Activity |
| --- | --- | --- |
| 4-7 Feb 2014 | Silver Spring, Ma, USA | MSDI Open Forum + MSDIWG 5 |
| 4-6 Mar. 2015 | London, UK | MSDI Open Forum + MSDIWG 6 |

Chair: Jens Peter HARTMANN, Denmark                       Email: jepha@kms.dk 
Vice-chair: Ellen VOS, Netherlands                              Email: em.vos@mindef.nl 
Secretary: John PEPPER, OceanWise                          Email: john.pepper@oceanwise.eu

11.	HDWG WORK PLAN 2015-16

Tasks

| A | Maintain and extend the definitions in the IHO Dictionary in French, English and Spanish (IHO Task 2.11.1) |
| --- | --- |
| B | Liaise with other IHO bodies preparing publications containing glossaries (IHO task 2.11.1) |
| C | Liaise with other organizations developing dictionaries and/or glossaries (IHO task 2.11.1) |
| D | Develop the Spanish language Wiki version of S-32 with commercial contract support (IHO Task 2.11.2) |

| Work item | Title | Priority H-high M-medium L-low | Next milestone | Start Date | End Date |  | Status P-planned O-ongoing C-completed S-superseded | Contact Person(s) * indicates leader | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.2 | Review all terms currently included in S-32 for their relevance in accordance with the S-32 Business Rules and propose which definitions should be removed from S-32 | M | a. Terms a – d b. Terms e – l c. Terms m – r d. Terms s – z | 2012 2012 2013 2013 | 2015 2015 2016 2016 | P P P P | All | S-32 |  |
| A.3 | Review the approved definitions of Altitude, Elevation and Height | H | TSMAD27 CSPCWG10 HSSC6 | 2012 | 2014 | O |  | S-32 | Alternative definitions to be submitted by HDWG to TSMAD27 (Dec 2013) and CSPCWG10 (Jan 2014) before endorsement |
| B.6 | CSPCWG - Aquaculture | H | MS‟ approval | 2011 | 2014 | O | All | S-32 | Proposed definition endorsed by HSSC5 |
| B.7 | CSPCWG - Phase of a navigational light | H | MS‟ approval | 2011 | 2014 | O | All | S-32 | Proposed definition endorsed by HSSC5 |
| B.8 | TWLWG - Mean sea level | H | HSSC6 | 2011 | 2014 | C | All | S-32, IHO Resolution 3/1919 | See Annex C of HSSC6- 05.9A. |
| B.9 | SNPWG - Underkeel clearance/allowance | H | MS‟ approval | 2011 | 2014 | O | All | S-32 | Proposed definition endorsed by HSSC5 |
| B.10 | IHB - Single Beam Echo Sounder | H | MS‟ approval | 2011 | 2014 | O | All | S-32 | Proposed definition endorsed by HSSC5 |
| B.11 | UKHO - Seafloor | M | HSSC6 | 2012 | 2014 | P | All | S-32 |  |
| B.12 | UKHO - Bathymetry | M | HSSC6 | 2012 | 2014 | P | All | S-32 |  |
| B.13 | TWLWG | H | Water Level Station | 2014 | 2014 | C | All | S-32, IHO Resolution 3/1919 | See Annex C of HSSC6- 05.9A. |

Meetings (IHO WP task 3.1.8)

No meetings have taken place. At HSSC5, the HSSC confirmed the need for a face to face meeting and invited the WG to act accordingly. Tbc in 2015.

Chair: Jean LAPORTE, France                         Email: jlaporte@shom.fr

Vice-Chair: Vacant                                         Email:

Secretary: David WYATT, IHB                         Email: adso@iho.int

12.	ABLOS WORK PLAN 2015-16

Tasks

| A | Organise the 8th ABLOS Conference in 2015 (IHO Task 2.12.2) |
| --- | --- |
| B | Maintain IHO Publication C-51 “Technical Aspects of the Law of the Sea (TALOS) Manual” (IHO Task 2.12.3) |
| C | Deliver a standard training program on the hydrographic aspects of maritime delimitation. (IHO Task 3.5.2) |
| E | Provide advice and guidance on the technical aspect of the Law of the Sea to relevant organizations, bodies and Member States. (IHO Task 2.12.3) |
| F | Organise and prepare the annual business meetings of ABLOS (IHO Task 2.12.1) |

| Work item | Title |  | Priority H-high M-medium L-low | Next milestone | Start Date | End Date |  | Status P-planned O-ongoing C-completed | Contact Person(s) * indicates leader | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Organise 8th ABLOS Conference | H | Begin advertising | 2013 | 2015 | 0 | All members of ABLOS through Niels Andersen* | N/A |  |
|  |  |  | Identify key note speaker | 2013 |  | 0 |  |  |  |
|  |  |  | Attract presentation abstracts | 2014 | 2015 | O |  |  |  |
| B.1 | Prepare draft 6th Edition of C-51 (TALOS Manual) for adoption by Member States | M H H | Generate draft new structure for chapter 3 Review contents of chapters and identify areas requiring revision | 2013 2014 2014 | 2016 2015 2015 | P O O | Chris Carleton* | IHO Publication C-51 |  |
| C.1 | Deliver standard training programmes for the CBSC | H |  | 2011 | Continuous | O | John Brown* |  | Workshops planned in 2015 in the CBSC Work Plan. |
| E.1 | Provide advice and guidance on the technical aspect of the Law of the Sea | H |  |  | Continuous | O | All members of ABLOS through the Chair |  |  |

Meetings (Tasks A & F)

| Date | Location | Activity |
| --- | --- | --- |
| 21 – 23 Oct 2014 | Copenhagen, Denmark | ABLOS 21 |
| 19 & 23 Oct 2015 | IHB, Monaco | ABLOS 22 and 8th ABLOS Conference |
| Oct 2016 | Korea (venue tbc) | ABLOS 23 |

Chair: Sunil BISNATH                              Email: sbisnath@yorku.ca

Vice-Chair:John BROWN                       Email: john.brown@ukho.gov.uk

Secretary: David WYATT                       Email: adso@iho.int

# 13. 	S-66 PROJECT TEAM WORK PLAN 2015-16

## Tasks

| A | Revise IHO Publication S-66 – “Facts about electronic charts and carriage requirements”. |
| --- | --- |

# Draft in preparation

# 14. 	COORDINATION WORK PLAN 2015-16

## Tasks

| A | As required, establish Working Groups to fulfil the Committee Work Plan, monitor their work and review annually the continuing need for each Working Group previously established by the Committee (HSSC TOR) |
| --- | --- |
| B | Provide technical advice and guidance on IHO technical standards (IHO Task 2.1.2) |
| C | Conduct the 2014 and 2015 meetings of HSSC (IHO Task 2.1.1) |

## Work items

| Work item | Task | Priority H-high M-medium L-low | Next milestone | Start Date | End Date | Status P-planned O-ongoing C-completed S-Superseded | Contact Person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Meetings (Task C)

| Date | Location | Activity |
| --- | --- | --- |
| 5-8 Nov 2013 | Shanghai, China | HSSC 5 |
| 11-14 Nov 2014 | Valparaiso, Chile | HSSC 6 |
| Nov 2015 (TBD) | TBD | HSSC 7 |
| Nov 2016 (TBD) | TBD | HSSC 8 |

HSSC Chair: Mathias Jonas, Germany	Email: Mathias.Jonas@bsh.de

HSCC Vice Chair: Mike Prince, Australia	Email: mike.prince@defence.gov.au

HSSC Secretary: Gilles Bessero, IHB 	Email: detch@iho.int

HSSC Assistant Secretary: Yves Guillam, IHB	Email: adcs@iho.int

# Footnotes

Allowing for approval via HSSC (in accordance with Resolution 2/2007) before MS and publication.