**ENCWG1-4A**

**LIST OF ACTIONS FROM HSSC-7**

| **AGENDA****ITEM** | **SUBJECT** | **ACTION****No.** | **ACTIONS****(in bold, action by)** | **TARGET****DATE/EVENT** | **STATUS****(at 11 Feb. 2016)** |
| --- | --- | --- | --- | --- | --- |
| **1. Opening and Administrative Arrangements**  |
| 1 | Contact List | HSSC7/01 | **IHO Member States** to provide the IHB with their updates to the HSSC List of Contacts. | **Permanent** |  |
| **3. Matters arising from Minutes of 6th HSSC Meeting** |
| 3 | Hydrographic Surveys Scoping | HSSC7/02 | **IHB** to issue a CL inviting IHO MS and Expert Contributors to participate in the work of the HSSC Hydrographic Surveys Scoping Project Team (H2S PT) created at HSSC-7. | **End of November 2015** | DONEIHO CL 83/2015dated 7 Dec 2015 |
| 3 | Hydrographic Surveys Scoping | HSSC7/03 | **HSSC Project Team on Hydrographic Surveys Scoping** to elaborate the scope of possible activities on hydrographic standards and publications and propose a way forward taking into consideration Doc. HSSC7-03C and proposal made by OGC to participate in the OGC Point Cloud Domain Working Group. | **HSSC-8** | On-going |
| **4. HSSC Administration** |
| **4.1 Implementation of Programme Performance Indicators** |
| 4.1 | HSSC Programme Performance Indicators (PIs)  | HSSC7/04 | Inputs to the current HSSC WPI for the 2014 period to be provided by **HSSC WG Chairs** (Performance Indicators No 2 and 3) and **WEND WG Chair** (Performance Indicator No 5) by 31 January 2016. | **31 Jan. 2016** | DONE |
| 4.1 | IHO Strategic Plan - IHO 3-year Programme of Work | HSSC7/05 | **Chairs of HSSC WGs** to collect the views of their members on the IHO Strategic Plan and the IHO 3-year Programme of Work | **By end of April 2016** | Planned |
|  |  |  | **HSSC Chair Group** to prepare inputs for the revision of the IHO Strategic Plan and the IHO 3-year Programme of Work | **June 2016** |  |
|  |  |  | **HSSC Chair Group** to prepare inputs for the revision of the IHO Strategic Plan and the IHO 3-year Programme of Work. | **HSSC-8** |  |
| **5. Reports by HSSC Working Groups** |
| **5.1 S-100 (S-100WG)** |
| 5.1 | IMO Performance Standards | HSSC7/06 | **S-100WG** to investigate and identify any amendments to existing IMO Performance Standards that may be required to use S-100 based products including S-101 ENCs. | **HSSC-8** | Planned |
| 5.1, 5.5 | S-100 Domains | HSSC7/07 | **NIPWG** to submit to the **S-100WG** a proposal relating to harmonization requirements within the different domains of the Feature Concept Dictionaries. | **February 2016** | DONE |
| 5.1 | Registry Manager | HSSC7/08 | **HSSC Members** to ensure that their country support the IHO budget for 2016 proposing to staff the S-100 Registry Manager position through a permanent IHB staff member (IHO CL 74/2015 refers). | **30 November 2015** | DONEIHO CL 88/2015 |
| 5.1 | Under Keel Clearance Management Information | HSSC7/09 | **S-100WG** to set up a project team for developing a product specification for under keel clearance management information | **HSSC-8** | Planned |
| 5.1 | Under Keel Clearance Management Information | HSSC7/10 | **IHB** to issue a CL inviting IHO MS and Expert Contributors to participate in the Under Keel Clearance Management Information Project Team (UKCM PT) created at HSSC-7, and provide support to the S-100WG accordingly. | **End of November 2015** | DONEIHO CL84/2015 dated 9 Dec |
| **5.3** **ENC Standards Maintenance (ENCWG)** |
| 5.3 | Working Groups’ Officers | HSSC7/11 | **ENCWG** to announce the potential vacancy for Vice-Chair in its call for the ENCWG-1 meeting. | **Dec. 2015** |  |
| 5.3 | S-58 | HSSC7/12 | **ENCWG** to submit for endorsement by HSSC draft Ed. 5.1.0 of S-58 and a proposal for the date of entry-into-force taking into account feedbacks received from industry, RENCs and ENC Producers.  | **End of March 2016** | Planned |
| 5.3 | S-58 | HSSC7/13 | Subject to HSSC endorsement, **IHB** to issue a CL to IHO Member States seeking their approval of the new Edition of S-58 and of its date of entry-into-force. | **HSSC-8** | Planned |
| 5.3 | S-52, S-64 | HSSC7/14 | **ENCWG** to co-ordinate with CIRM and IEC a well-founded proposal revising the timeline for the withdrawal of Ed. 6.0 of S-52, Ed. 3.4 of the Presentation Library and Ed. 2.0.0 of S-64. | **End of February 2016** (for information at NCSR-3) | On-going |
| 5.1, 5.3 | Portrayal of Lengths of Sector Lights | HSSC7/15 | **S-101 Project Team** to consider the proposal submitted by the Norwegian Coastal Administration on the portrayal of lengths of sector lights (Doc. HSSC7-05.1C). | **HSSC-8** | Planned |
| **5.4 Revision of S-66** |
| 5.3, 5.4 | S-66 | HSSC7/16 | **S-66 Project Team** to submit a draft revision of S-66 (Stage 1) to the ENCWG, followed by submission for endorsement by HSSC in April by correspondence. | **March 2016 (ENCWG-1)****April 2016** | Planned |
| 5.4 | S-66 | HSSC7/17 | Subject to HSSC endorsement, **IHB** to issue a CL to IHO Member States seeking their approval of the new Edition of S-66. | **May 2016** | Planned |
| **5.5 Nautical Information Provision (NIPWG)** |
| 5.5, 5.6 | S-1xx Portrayal Issues | HSSC7/18 | **NCWG** to compile portrayal requirements relating to product specifications in general as part of its programme of work. | **NCWG-2** | Planned |
| 5.5 | S-1xx Portrayal Issues | HSSC7/19 | **NIPWG** to experiment a workflow with stakeholders (industry, academia, …) and other HSSC WGs (S-100WG, DQWG, …) for S-122 portrayal issues. | **HSSC-8** | Planned |
| 5.5 | S-122 test beds | HSSC7/20 | For S-122, and assuming that sufficient information is available, **NIPWG,** in liaison with NCWG and S-100WG, to make use of test beds opportunities (e-navigation projects as appropriate). | **HSSC-8** | Planned |
| **5.6 Nautical Cartography (NCWG)** |
| 5.6 | Working Groups’ Officers | HSSC7/21 | **NCWG** to announce the potential vacancy for Vice-Chair in its call for the NCWG-2 meeting. | **Jan. 2016** | Planned |
| 5.6 | S-11 Part A | HSSC7/22 | **NCWG** to re-consider S-11 Part A for addressing ENC scheming issues in a separate section and submit a new draft to HSSC. | **NCWG-2****HSSC-8** | Planned |
| 5.6 | S-4 | HSSC7/23 | **IHB** to issue a CL to IHO Member States seeking their approval of S-4 Ed. 4.6.0. | **(End of Nov. 2015)** | DONE(IHO CL 92/15) |
| 5.1, 5.6 | AIO | HSSC7/24 | **S-101 PT** to address the need for improved functionality regarding T&P updates in future ENC/ECDIS. | **HSSC-8** | Planned |
| **5.7 Data Quality (DQWG)** |
| 5.2, 5.7 | Data Supply Chain Certification | HSSC7/25 | **DQWG** and **DPSWG** to develop their views on Data Supply Chain Certification (Jeppesen’s presentation at HSSC-7 refers) at their next meetings. | **May 2016** | Planned |
| **5.8 Tides, Water Level and Currents (TWCWG)** |
| 5.8 | Implementation of transition arrangements | HSSC7/26(former HSSC6/07) | **TWCWG** to consider the need for creating an S-111 Project Team (in liaison with **S-100WG**). | **TWCWG-1** | Planned |
| 5.8 | Resolution 3/1919 | HSSC7/27 | **IHB,** in liaison with **TWCWG Chair,** to issue a CL to IHO Member States seeking their approval of the revised draft Resolution 3/1919, taking into account IHB comments (Doc. HSSC7-05.8C refers). | **December 2015** | On-going |
| **5.9 Hydrographic Dictionary (HDWG)** |
| 5.1, 5.9 | Future of S-32 | HSSC7/28 | **S-100WG** to provide the HDWG with its generic technical specifications / requirements in terms of definitions, register(s) and procedures. | **May 2016** | Planned |
| **6. Inter-Organizational Bodies** |
| **6.1 Advisory Board on the Law of the Sea (ABLOS)** |
| 6.1 | C-51 | HSSC7/29 | **IN** to submit a proposal to ABLOS on the need to expand the scope of C-51 in relation with judgments.  | **ABLOS-23** | Planned |
| 6.1 | S-121 – Maritime Limits and Boundaries | HSSC7/30 | Considering that the IHO S-121 Product Specification will not be approved before end of Dec. 2017, **IHB** to inform DOALOS (**in liaison with ABLOS Chair**) of the expected date of approval of S-121. | **End of Nov. 2015** | DONEIHB Letter dated 15 Dec 2015 |
| 6.1 | S-121 – Maritime Limits and Boundaries | HSSC7/31 | **IHB** to issue a CL inviting IHO Member States to support the development of S-121 product specification within a project team under the S-100WG. | **End of Nov. 2015** | DONEIHO CL84/2015 dated 9 Dec |
| **7. Decisions of other bodies affecting HSSC** |
| **7.1 IRCC (incl. MSDIWG)** |
| 5.3, 7.1 | S-65 | HSSC7/32 | **ENCWG** to review S-65 for alignment with the WEND Principles and Guidelines as amended. | **HSSC-8** | Planned |
| 5.1, 7.1 | S-102 | HSSC7/33 | **Chair of S-102** **PT** to consider the issues of interoperability with SDI standards (such as INSPIRE elevation data specification, etc.). | **HSSC-8** | Planned |
| 7.1 | Repository of S-100-based product specifications | HSSC7/34 | **IHB** to maintain the list of S-xxx product specification and make it available on the IHO webpage including use-cases and business-cases, as appropriate. | **Permanent** | Planned |
| **7.2 IMO** |
| 5.5, 7.2 | Harmonized display of navigation information | HSSC7/35 | **NIPWG** to coordinate the contribution of the IHO to the development of guidelines for the harmonized display of navigation information and to the preparation of the output related to the development and implementation of maritime service portfolios (MSPs), notably in liaison with the WWNWS-SC. | **HSSC-8** | On-going |
| 5.1, 5.5, 7.2 | Harmonized display of navigation information | HSSC7/36 | **S-100WG** to prepare, in liaison with **NIPWG**, the **IHB** and the **HSSC Chair**, a submission on the contribution of the S-100 framework to the harmonized display of navigation information and the impact on existing performance standards for consideration by NCSR 2 (deadline: 25 Dec 2015). | **18 Dec. 2015** | DONE (IMO NCSR 3/9 refers) |
| 5.1, 5.3, 7.2 | E-navigation implementation | HSSC7/37 | **ENCWG and S-100WG** to monitor any possible impact of the work on the agreed e-navigation outputs on ECDIS related standards and S-100 related standards respectively. | **HSSC-8** | Planned |
| 5.3, 7.2, 7.5 | ECDIS Performance Tests | HSSC7/38 | **ENCWG** to consider the impact of the implementation of the new editions of S-52, S-52 Presentation Library and S-64 on the ECDIS ship check dataset and associated instructions taking into consideration the new ECDIS Chart 1. | **ENCWG-1** | Planned |
| 5.2, 7.2 | Maritime cybersecurity | HSSC7/39 | **DPSWG** to monitor the development of the industry guidance on maritime cybersecurity and to advice on possible future actions. | **HSSC-8** | Planned |
| 5.5, 5.6, 7.2 | Polar Code | HSSC7/40 | **NIPWG and NCWG** to consider improvements to current IHO specifications or other actions which could facilitate the implementation of the provisions of the Polar Code related to charting issues (Part I-B, Additional Guidance to Chapter 9 (Safety of Navigation) refers). | **HSSC-8** | Planned |
| 5.1, 5.5, 7.2 | Unique Identifiers | HSSC7/41 | **NIPWG and S-100WG** to consider referring the issue of Unique Identifiers to the IMO-IHO Harmonization Group on Data Modelling and report to HSSC-8 (see Action HSSC7/42). | **HSSC-8** | On-going |
| **7.6 IALA** |
| 5.1, 7.6 | Unique Identifiers | HSSC7/42 | **IALA** to submit its requirements on Maritime Resource Name scheme to the S-100WG (see Action HSSC7/41). | **Prior to S-100WG-1** | Planned |
| **7.7 ISO** |
| 7.7 |  | HSSC7/43 | **IHB** to raise, in the liaison report to the 41st meeting of ISO TC211, the issue of stability of standards and the impact on derived standards of the ISO updating process (Doc. HSSC7-07.7B INF7 refers). | **December 2015** | On-going |
| **7.12 ICPC** |
| 7.12 | ICPC | HSSC7/44 | **IHB** to staff the draft MoU proposed by the ICPC in liaison with relevant HSSC WGs. |  | On-goingIHO CL 85/2015 dated 9 Dec |
| **7.13 DGIWG – NATO GMWG**  |
| 5.1, 7.13 | AMLs | HSSC7/45 | **S-100 Registry Manager** to process the request for the establishment of a domain for Additional Military Layers (AML) in accordance with S-99. | **S-100WG-1** | Planned |
| 7.13 | AMLs | HSSC7/46 | **UK** to ensure that the approval process of NATO STANAGs related to AMLs is compatible with the IHO process for standards approval. | **HSSC-8** | Planned |
| **9. Liaison with External Stakeholders** |
| 9 | Outreach | HSSC7/47 | **IHO Member States** to consider representing IHO interests in the stakeholders’ meetings organized by Digital Ship and inform the IHB of their intentions. | **December 2015** | Planned |
| 7.5, 9 | Outreach | HSSC7/48 | **IHB** to liaise with the CIRM Secretariat for the possible organization of an ECDIS Forum at the CIRM Annual Meeting, 2016. | **December 2015** | On-going |
| **10.**  **Review and Endorsement of HSSC Work Plan and List of Actions** |
| 10 | Status of IHO Publications | HSSC7/49 | **IHO Member States** to provide their additional requirements, if any, and contributions for translation in French and/or Spanish of IHO Publications (Doc. HSSC7-10A refers). | **Permanent** | Planned |
| **11. Any Other Business** |
| 5.3, 7.1, 11 | EU Marine Equipment Directive  | HSSC7/50 | **IHB** to ensure that the ENCWG is kept informed on the outcome of the IENWG work item related to the revision of the EU Marine Equipment Directive. | **ENCWG-1** | PlannedOn-going |