## Slide 1: 4th IHO-EU Network WG Meeting
EMODnet Coastal Mapping
SHOM
gael.morvan@shom.fr

## Slide 2: Objectives
Assess the current availibility of digital coastal maps in the EU
Disseminate this information by EMODnet
Share experience of coastal mapping in the EU
Develop standards for best practices
Propose how a future JECMaP could operate

## Slide 3: Deliverables
Every 2 months : progress report
After 6 months : first version of portal on-line
After 9 months : interim report
  Summary of challenges involved in preparing portal
  Results of task 2(d)i :
  Listing and summarizing past experience indicating at least cost, depth range, turbidity, furthest distance from coast, vertical and horizontal tide range.
  Results of task 2(d)ii :
  Developing and testing an algorithm for choosing most appropriate surveying method.

## Slide 4: Deliverables
After 18 months :
  final version of portal on-line
  final report
  executive summary of final report
After 20 months : stakeholder workshop
After 36 months : maintenance report

## Slide 5: Consortium
Hydrographic offices :
FRANCE – BELGIUM – GERMANY – GREECE – IRELAND – ITALY – LATVIA – NORWAY – PORTUGAL – SLOVENIA – SWEDEN
Regions :
CPMR – Regione Lazio
Public Bodies :
ISPRA – RWS - GeoEcomar – DDNI
IT company :
Worldline
Observers
Hydrographic offices :
UNITED KINGDOM - SPAIN

## Slide 6: Organisation

## Slide 7: Meetings
  Kick-off : 24th June 2015
  Specification review (M3) : 21st-22nd October 2015 (EMODnet Jamboree)
  Portal (M5) : 1st-2nd December 2015
  Algorithm (M9) : early March 2016
  Interim (M12) : June 2016
  Interim (M16) : October 2016
  Final (M18) : December 2016 – Brussels
  Stakeholder (M20) : Feb. 2017 – To be defined

## Slide 8: WP1 : Digital Mapping

## Slide 9: WP1 progress :
Forum (partners only)
Specifications of the portal : validated in Ostend!
Implementation of the portal itself : done!
  Opening to the partners : 18th December
  Public opening : 23rd December
Training activities
  1st training organized during the algorithm meeting (03/2015) for the partners only
  One or more trainings later for other users

## Slide 10: About the portal (1st release) :
Direct access from the website
Default projection EPSG:3035 (ETRS89/ETRS-LAEA)
Can be changed to EPSG:4326 (WGS84) or EPSG:3857 ‘Web Mercator)
Basic Tools for the first release
Data initialization in progress
WMS and WFS available (WCS later)

## Slide 11
Services
Dissemination services
Internet
Access Control Layer
Partner Administrator
Identity Control Layer
Backend
Data Warehouse
Access Control Management
Behind the Portal:

## Slide 12: WP2 : Share Experience, Standards and Best Practices

## Slide 13: WP2 progress (1/2) :
Assess consistency of the existing vertical datum
  Inventory of the used vertical references : in progress
  Inventory of available transformations and current developments (national projects) : in progress (survey)
Listing and summarizing of past experiences
  Survey on-line(operated by Lime Survey)
  Informations on area and on survey
  Communicated to the partners and other operators
  To be filled in before end of January

## Slide 14: WP2 progress (2/2):
Development of an algorithm to help the coastal survey planning at regional level
  Coastal Mapping Planner (CMP) basic concepts elaborated
  CMP decision tree will use the fuzzy logic
Build a technical and economical strategy
  Refinement of the algorithm by adding the cost analysis – not yet started
Sharing plateforms
  compilation of the partners contributions in progress

## Slide 15: WP3 : Future programme

## Slide 16: WP3 progress (1/2):
Inventory of the current economic models
  Common survey with Governance topic
Current EU fundings
  Template for analysis – Selection of regions – in progress
  Analysis of the transnational programmes – in progress
  Analysis of the research framework programme – in progress
Governance of bathymetric data management
  Survey analysis in progress (already filled in by most of the partners)

## Slide 17: WP3 progress (2/2) :
Validation of the programme
  Inventory of the tools : Initiatives related to coastal areas (Bologna Charter, Intercoast, Facecoast, TNEC,…)
  Inventory of the needs : coastal protection, ICZM, deposits management…
Future programme
  Not started – will result from the other tasks.

## Slide 18: Thank you!