LIST OF ACTIONS FROM WENDWG-4

Status as of 10 Feb. 2015

| Number | Action | Responsible | Agenda item | Deadline | Status/Remarks (Feb. 2015) |
| --- | --- | --- | --- | --- | --- |
| WENDWG4/01 | update the WENDWG Membership in the IHO website | Secretary | 1 | May 2014 | Done. Task Group and RENC Harmonization Sub-Group added |
| WENDWG4/02 | further develop doc. WENDWG4-03C (draft procedure for resolving overlapping ENC data) in order to reflect the Guidelines | Task Group | 3 | 15 April 2014 | Done |
| WENDWG4/03 | submit the draft procedure for resolving overlapping ENC data developed under Action 2 to IRCC6 | Chair | 3 | IRCC6 | Done. Presented as IRCC6-08C |
| WENDWG4/04 | develop a proposal for a pilot project using OEM software tools to resolve overlapping ENC data issues and submit it to the WENDWG | Singapore | 3 | WENDWG5 | Done. HSSC6-05.6B refers. |
| WENDWG4/05 | submit the paper on Guidelines on Assessing and Eliminating the Risk of Overlapping ENC Cells (doc. WENDWG3-05) to IRCC6 | Chair | 3 | IRCC6 | Decision IRCC6/15 (RENCs to first use the procedure on overlaps as an IRCC procedure until more input is received and then possibly propose this to be an IHO resolution) |
| WENDWG4/06 | provide a revised RHSG paper on WENC (doc. WENDWG4-04C Annex B) to the Chair | RHSG | 4 | April 2014 | Done |
| WENDWG4/07 | submit a report on the development of the WENC Concept to IRCC and seek subsequent endorsement by Member States | Chair | 4 | IRCC6 | Done. Action IRCC6/30 to report on the WENC concept to IRCC7 |
| WENDWG4/08 | propose the minimum standards for RENC operation considering CL05-2012 and the paper provided by US-Canada on actions from RHSG1 | RHSG | 4 | April 2014 | Cancelled (tbc) |
| WENDWG4/09 | continue working to attract ENC producer nations to join the RENCs | RENCs | 4 | Permanent | Done |
| WENDWG4/10 | produce a paper on the benefits for ENC producer nations to join a RENC | RHSG | 4 | April 2014 |  |
| WENDWG4/11 | provide the ENC coverage report to WENDWG | RENCs | 5 | WENDWG5 |  |
| WENDWG4/12 | provide the statistics on those ENCs not distributed via RENCs | RENCs | 5 | WENDWG5 | Done. Replaced by IHO CL 59/2014 (ENC distribution census) |
| WENDWG4/13 | provide a scoping paper of the ENC Catalogue | IHB | 7 | August 2014 | Done. |
| WENDWG4/14 | provide comments to the Chair on the necessary items to progress the ENC catalogue | WENDWG members | 7 | 1 October 2014 1 December 2014 | Done (CA and US). |
| WENDWG4/15 | specify the necessary items to progress the ENC catalogue and provide feedback to the IHB | Chair | 7 | 1 December 2014 WENDWG5 |  |
| WENDWG4/16 | request IRCC to task MSs to provide information on the ENCs that are not available through a RENC | Chair | 7 | During IRCC6 | Done. IHO CL 59/2014 refers. |