## Slide 1: SPRWG Proposed orientations
IHO Council

## Slide 2
Smart Goal 1: Evolving
the support of safe and efficient navigation
CONVENTION: object of the IHO
Standardization
Coordination & Cooperation
SG-2: Developing use of marine environment geospatial inf. for societal benefits
Smart Goal 3: Promoting IHO as a key partner on the Ocean scene
Capacity Building
Communication
STRATEGIC
PLAN
IMPLEMENTATION
Performance Indicator-x
Strategic Target-y
PI-z
ST-x
PI-y
ST-z
PI-t
PI-x
ST-y
ST-z

## Slide 3: Proposed management plan (1/2)
October 2018 C-2 orientations on the general structure of the Strategic Plan
End January 2019 2 days meeting of drafting groups in Monaco
March 15th Draft Goals/Targets/Performance indicators transmitted to IHO Secretary General, HSSC chair and IRCC chair for evaluation and comments
On-going Strategic Plan drafting continues
Beginning of May HSSC and IRCC provide feedback to SPRWG

## Slide 4: Proposed management plan (2/2)
3, 4 or 5 June Special SPRWG Inter-sessional meeting (in conjunction with IRCC-11)
June HSSC & IRCC submit proposal to develop the WP 2021- 2023 (ref. IHO-R 12/2002)
July-August SPRWG submits proposed IHO SP to C-3 (3 months before C-3)
October C-3 reviews proposals on SP, WP & budget (ref. IHO-R 12/2002)
November Council Report, including proposed SP, submitted to A-2
April 2020 A-2

## Slide 5: Action requested of the Council
Note the report of the SPRWG;
Decide to continue the working group
Task the working group to develop the SP on the basis of smart goals, that can be assessed through a limited number of strategic targets and PIs
Endorse the management plan for the drafting phase
Include Secretary General in the membership
Encourage IHO member States to participate to the SPRWG
Take any other action considered appropriate