## Sheet1
MMSDIWG Work Plan
2019-10-16
Work Item | Work Activity | Milestones | Start Date | End Date | Status P:Planned O:Ongoing C:Completed S:Suspended | Comments
1 | Drafting committee to develop new Terms of Reference (TOR) for the MMSDIWG. | * Solicit volunteers for the Drafting Committee; * Draft TOR; * Distribute TOR for wider comment from the MACHC; * Approve new TOR | 2018-12-01 | 2019-04-01 | C | TOR was approved after the MACHC comment period in March 2019.
2 | MMSDIWG to develop a List of Layers common to varios MSDI project users in the MACHC Region. | * Determine the common layers needed; * Develop list; * Use list to support MSDI efforts in the Region | 2019-04-01 | 2019-07-01 | C | Bathy, Shoreline, Maritime Boundaries defined as key foundation datasets
3 | MMSDIWG to create an MSDI Inventory of existing MSDI / SDI web resources in the MACHC Region. | * Explore Inventory methods; * Develop Inventory questions; * Create Inventory tool for gathering MSDI information; * Notify MMSDIWG members about MMSDIWG Inventory; * Gather MMSDIWG results; * Make the MACHC members MSDI website information available via the MACHC MMSDIWG webpage | 2019-07-01 |  | O | Questionairre sent to all members (MMSDIWG Inventory Survey) and results are now displayed via the MMSDIWG site. Ongoing requirement to maintain and to fill in the gaps.
4 | MMSDIWG to identify potential projects to support within the MACHC Region. | * Identify potential projects in the MACHC Region; * Develop a list of possible projects; * Engage with project teams; Determine ways the MMSDIWG could support the project to grow MSDI within the Region | 2019-10-01 |  | O | Disaster Relief - Hurricanes; Risk Assessment - Dawn Seepersad
5 | MMSDIWG to explore potential partnerships within the MACHC Region. | * Identify exisiting SDI / MSDI efforts within the Region; * Develop a list of possible partners; * Engage with possible partners; * Determine best way to partner to support MSDI in the Region |  |  | O | CMA - Caribbean Marine Atlas (https://www.caribbeanmarineatlas.net/). Several member states host data on the CMA web portal.
6 | MMSDIWG to explore potential Capacity Building efforts with MSDI in the MACHC Region. MSDI Training at the MACHC Seminar in December 2019. | * Determine possible MSDI Capacity Building efforts; * Identify the logistics necessary for an MSDI CB effort; * Develop MSDI CB effort plan; * Implement MSDI CB effort |  |  | O | Capacity Building MSDI Training will take place on Tuesday 03 DEC 2019 prior to the MACHC Plenary Meeting.
7 | MMSDIWG to determine the MMSDIWG Vice Chair | * UKHO volunteered to provide a Vice Chair Candidate at the MACHC Meeting; * UKHO to identify a candidate | 2018-12-01 | 2019-07-01 | C | Tom Scott-Clarke from the UKHO has filled the position of the MMSDIWG Vice Chair.
8 | MMSDIWG to determine and develop any required MSDI governance documents. | * Review exisiting MSDI Governance documents; * Draft MMSDIWG Governance document; * Share the Draft with the MMSDIWG members for comment; * Get consensus / approval from MMSDIWG members | 2019-07-01 | 2019-10-01 | C | Tom Scott-Clarke from the UKHO has drafted a MMSDIWG Governance Document. Completed Governance Document endorsed at the MMSDIWG Meeting on 02 OCT 2019.
9 | Promote MSDI Discoverability within the MACHC Region | * Identify MSDI resources within the Region; * Build list of MSDI resources; * Make list of MSDI resources available via MACHC MMSDIWG webpage; * Share list of MSDI resources with other MSDI venues |  |  | O | MSDI Resources have been listed and linked on the MMSDIWG Site to aid data discoverability.
10 | Promote MSDI efforts within the MACHC Region | * Identify ways to socialize MSDI efforts within the MACHC Region; |  |  | P
11 | Conduct Quarterly MMSDIWG Meetings each year | * Plan three Quarterly MMSDIWG Meetings via telecon / webmeeting connections; * Plan one Quarterly Meeting at the MACHC Meeting in person; * Determine if more MMSDIWG Meetings are necessary to accomplish the objectives and work plan |  |  | O | MMSDIWG Meeting information to include the Agenda and Minutes are available on the MACHC Initiatives website.
12
13
14